## Chart by Area
Count of Priority (High, Medium, Low, Closed) | Priority (High, Medium, Low, Closed)
Business Area / Process | Closed | High | Low | Medium | Grand Total
Accts Rec |  | 1 |  | 1 | 2
BDMS | 2 |  |  |  | 2
Fin Aid | 1 | 6 |  | 6 | 13
Finance | 7 | 2 | 1 | 3 | 13
General | 3 | 1 |  | 1 | 5
HR | 2 | 9 |  |  | 11
Integration |  | 2 | 1 |  | 3
Luminis | 3 | 4 |  | 4 | 11
ODS | 2 |  |  | 3 | 5
Overall | 4 | 8 | 2 | 4 | 18
Student | 1 | 3 |  | 5 | 9
Technical | 1 | 4 |  |  | 5
Grand Total | 26 | 40 | 4 | 27 | 97

## Issue Open Items Log
Business Area / Process | Priority (High, Medium, Low, Closed) | Date Opened | Date Resolution Required (Red Cell Denotes Past Due) | Date Resolved (or month) | Issue/Open Item and Comments | Follow-up To Be Completed By
Fin Aid | High | 2009-02-27 | 2009-03-17 | Required? Completed? | Decide when to start bringing in 09/10 ISIRS into training environment. Recommended to do this during the first Consulting visit scheduled for 3/24/09 First test in PROD of 0910 is to occur starting 10/30/2009. On track or stale project activity? (Comment added 7/31/2009) | FinAid Implementation Team
Fin Aid | High | 2009-06-05 | 2009-07-14 |  | Review RPRAUDT consider how to count grades that are W – Withdrawal after the end of add/drop…Must work with Instructional business area to follow the process model. Updated 7/27/2009 | FinAid Implementation Team and Student Implementation Team--Instructional Area…Lydia Hearn to provide input.
HR | High |  | 2009-07-23 |  | Decision on pooled positions | Henry and Kim
Overall | High |  | 2009-07-31 |  | Posting of proprietary trip reports on FHDA internet site D Treacy --Was 'closed' reopened 7/16 (meeting has since been scheduled): It was raised to my attention, again as a result of a client crawl of the web, confidential and proprietary documents are being posted and are easily accessible via the web. This time it was http://fhdafiles.fhda.edu/downloads/eis/FHDATRFinTechTrainingShah200.doc As I noted below, if you access http://fhdafiles.fhda.edu/downloads/eis/ you encounter the 403 Forbidden error noting that I do not have permission to access the server. However, it appears the documents are being posted allowing access by the ‘world’. These need to be either locked down to internal (intranet) access only or password protected. (The latter may be easier to configure and still allow offsite access by staff.) Update week of 7/27--Drake and Kari working on technique to lock down site. | Chien Shih
Finance | High |  | 2009-08-03 |  | Approval queue process to be implemented in production (Finance). Carmen raised that approvals are not working; however, Chien explained that Hector is targeting 8/3/2009. Updated 7/27/2009 | Hector Quinonez
Technical | High | 2009-07-30 | 2009-08-03 |  | Schedule SunGard Higher Education Resource to assist with catalog/schedule conversion (3 days onsite) | Deb Treacy
General | High |  | 2009-08-06 |  | Handling of duplicate records 1-day workshop to outline decisions needed--to occur week of 8/3 (Update 7/26/2009) | Linda Wooden
Integration | High | 2009-07-16 | 2009-08-07 |  | Identify SunGard Higher Education Integration Service Requirements | Chien Shih, Deb Treacy
Technical | High | 2009-07-24 | 2009-08-07 |  | Identify resources for the conversion effort and determine need for supplementing to meet project milestones | Chien Shih, Deb Treacy
Finance | High |  | 2009-08-12 |  | Critical finance reports for first month end…Bob Barr explains those identified as critical on report inventory that was created June 2009 have been fulfilled (updated 7/30/2009) Two hours will be taken from the ODS session the week of 8/24 to strategically discuss and provide input to the reports required. Bob Barr notes critical reports are being addressed (updated 7/30/2009). | Deb Treacy
HR | High | 2009-07-24 | 2009-08-12 |  | Need to revisit SunGard Higher Education consulting support/resources assigned | Chien Shih, Deb Treacy
HR | High |  | 2009-08-13 |  | Budgeting/encumbering; lapsing requirements to be critiqued (fulfilling) (possible 'bolt on' application to fulfill needs; spreadsheet budgeting functionality (?)) (Update 7/26/2009) | Chien Shih
Overall | High |  | 2009-08-14 |  | International (SEVIS) processing – licensing, handling by campus D Treacy Feedback: "Depending on how configured they may need to report separately to the Bureau. Based on this thread it leads me to believe that they have two distinct INS institutional numbers and would need to do two separate submissions (not combined)." NOTE: sevisconnection amendment will possibly be needed as a contract amendment. K Moberg e-mail 7/21/2009: We were wondering if we have subscribed to SEVISTA with our Banner contract? This allows the international student offices to batch upload their student info to the Dept of Homeland Security and then receive confirmation back from them. FH currently enters each app manually, and DA uses FSA Atlas. FH probably could use SEVISTA to reduce manual processing. | Deb Treacy, Chien Shih, Student Core Team Leads
Accts Rec | High | 2009-07-14 | 2009-08-15 |  | Course fees built without any corresponding FOAPAL behind them in TST8 | Nancy Chao
Fin Aid | High | 2009-07-27 | 2009-08-15 |  | Need for a September 2010 session to support Financial Aid activities--first major disbursement. | Deb Treacy
Fin Aid | High | 2009-07-04 | 2009-08-17 |  | Return of Title IV – Meet with Student team to decide how to manage the total withdrawal field on SFAREGS | FinAid Implementation Team and Student Implementation Team
Fin Aid | High | 2009-07-04 | 2009-08-17 |  | Student Employment – Meet with HR/Payroll to create procedures for managing student employment. Decide whether to use a Pooled position | FinAid Implementation Team and HR/PR Implementation Team
Technical | High | 2009-07-27 | 2009-08-21 |  | Carlsbad/AbTech Banner disaster recovery environment configured. Randy Teschner to be providing mentoring support. | Tom Roza
HR | High |  | 2009-08-31 |  | 10/11/12 tax processing--Cyd Hawkins Recommendations. Analyzing extent of localizations required to combine 'payrolls'--payid events in Banner (taxation requirements) Customization Analysis to commence 8/3/2009 with recommendations delivered 8/7/2009. FHDA Decision by 8/31/2009 Required. (Update 7/26/2009) | Deb Treacy, Chien Shih, Kim Chief Elk
HR | High | 2009-07-13 | 2009-08-31 |  | Liquid Office Requirements | Kim Chief Elk, Chien Shih
HR | High | 2009-07-13 | 2009-08-31 |  | Clarification of technique/process to adapt Cyd Hawkins' recommendations for meeting FHDA CCD payroll/budgeting needs in Banner (stemming from 6/30/2009 meeting. Unable to implement during week of 7/6/2009.) | Deb Treacy, Jeff Greer
HR | High |  | 2009-08-31 |  | PeopleAdmin interface – purchase or locally develop? Meeting to occur morning of 7/30/2009 w/PeopleAdmin Representative. (Update 7/26/2009) Mtg results: Goal is to have functionality in place no later than November 2009. Most cost effective, efficient manner to implement will be critiqued. Presently 'free' flat, csv format obtained, new hire data extracted and manually keyed into Plus. Currently the # of new hires is not a significant. (Updated after mtg 7/30). | Kim Chief Elk, Chien Shih, Deb Treacy
HR | High | 2009-07-13 | 2009-08-31 |  | Web Time Entry--syncing and coordinating requirements | FinAid Implementation Team and HR/PR Implementation Team
Luminis | High | 2009-07-27 | 2009-08-31 |  | Channels for Student, Financial Aid and HR/PR must be identified/refined. Identify when they need to be incorporated in a pre-production environment (at what point). | Kurt Hueg
Luminis | High | 2009-07-30 | 2009-08-31 |  | Identification of Banner environment the Luminis test/development instance should be pointed to for system regression/user acceptance (Mock) testing. | Deb Treacy
Student | High |  | 2009-09-01 |  | CCCApply integration requirements analyzed (Sierra College as interim option) Funding has been secured for 1.5 years for implementing and maintaining CCCApply. Project schedule must be critiqued to bring 'test' integrated functionality in after baseline admission tests (updated 7/30/2009). | Chien Shih
Overall | High |  | 2009-09-01 |  | Mix of Banner 7/8 instances--9/1/2009 target for 'rehearsal' completion | Linda to coordinate move of Finance from 7
Fin Aid | High | 2009-07-27 | 2009-09-15 |  | Coordinate timing for Student and Fin Aid Mock business processing. Also, coordinate students to be built in Student Mock scenarios (allowing for Fin Aid to process students that are registered, etc.). | Deb Treacy, SunGard Higher Ed resource, Cindy Castillo, Kathleen Moberg, Lydia Hearn
Technical | High | 2009-07-29 | 2009-09-30 |  | Configuration change/management log/process created capturing all changes to the environment. | Tom Roza; Joe Lampo
Overall | High |  | 2009-09-30 |  | Coodinating campus-wide end user training--Initiating Plan and Accountability. Identify primary contact/coordinator. | Core Team
Overall | High | 2009-07-13 | 2009-09-30 |  | Impact of introduction of Banner/UDC model on the Business Process--Business Process modeling in the new enterprise framework. Possible impact on (employee) position requirements | Core Team
Integration | High | 2009-07-15 | 2009-10-01 |  | Resource 25 Purchased and ready for integration requirements | Chien Shih
Overall | High | 2009-05-27 | 2009-10-01 |  | Faculty Load 3-->4 decimal precision/scale for Student and HR/Payroll Requirements--"Mini Summit" facilitated 6/29/2009. Results/Options being compiled. | Deb Treacy; Chien Shih
HR | High | 2009-07-27 | 2009-10-30 |  | Script to be analyzed, designed to deploy benefits requirements--must have in place for monthly benefit changes. | Kim Chief Elk, Chien Shih
Overall | High | 2009-07-30 | 2009-10-30 |  | Requirement to have ability to 'brand' SSB for employees was raised. Need to have the WebTailor session redone (onsite). | Chien Shih; Deb Treacy
Student | High |  | 2009-10-31 |  | CCCApply implementation by November Critique SRT/UAT requirements ensuring baseline admissions functionality is FULLY tested prior to introducing integration to the common application system. (Update 7/30/2009) | Kathleen Moberg
Luminis | High | 2009-07-30 | 2010-03-31 |  | Replicate current faculty portal functionality in Luminis/SSB. | Kurt Hueg; Chien Shih
Luminis | High | 2009-07-30 | 2010-04-30 |  | Process for automating communication to students via Luminis or e-mail. Eliminating use of Population Selections. | Kurt Hueg; Chien Shih; Kathleen Moberg
Student | High | 2009-07-30 | 2010-04-30 |  | Students must have the ability to e-mail unofficial transcripts from either Luminis or SSB. (Current TouchNet functionality) | Chien Shih; Kathleen Moberg
Overall | High |  |  |  | GP Synch continues as long as Plus SIS is system of record | Jim
Fin Aid | Medium | 2009-02-27 | 2009-03-17 | Completed? | Decide how to manage and post any outputs from Banner that you want to share with the college FA staff. We talked some about printing out reports, posting them on a shared drive etc. | FinAid Implementation Team
Fin Aid | Medium | 2009-02-27 | 2009-03-17 | Completed? | Review the document ‘ FA Interface’ as a guide to working with the STUDENT team to identify and begin to build the Tables in the other System that apply as discussed . | FinAid Implementation Team
Fin Aid | Medium | 2009-05-01 | 2009-06-01 | Completed? | Review the FA email type with the Student team to determine how students may update that email address | FinAid Implementation Team
Accts Rec | Medium |  | 2009-08-31 |  | Dottie recommends an additional session after the 1st of the year | Deb Treacy
Fin Aid | Medium |  | 2009-08-31 |  | Separation of workstudy earnings by campus; student employment processing | Carol Linsley will work with Ken Whitelaw in August
Fin Aid | Medium |  | 2009-08-31 |  | SQL expertise for development of SAP rules Sheila now owns the process. Training for the functional area has occurred. Updated 7/27/2009…issue raised with timing of testing. NOTE: SRT/UAT with the student mocks? | Joe Lampo
Finance | Medium |  | 2009-08-31 |  | Prompt invoices – reverted to manual entry in Banner environment--See Maas/Banner Interface. | Joe Lampo/Hector Quinonez
Finance | Medium | 2009-06-30 | 2009-08-31 |  | Maas/Banner Interface--Email/details sent to Chien. | Hector, Joe, Deb Treacy/Chien Shih
Student | Medium |  | 2009-09-01 |  | Separate Instructional Support and Registrar functions in implementation tasks | Deb Treacy and Student Implementation Teams
Fin Aid | Medium | 2009-07-04 | 2009-11-30 |  | Work with Jeff Greer and Ken Whitelaw to determine how to move the correct payroll figures into the correct term for each college since the district will be running a combined payroll. | Carol Linsley, Jeff Greer, Ken Whitelaw
Student | Medium |  | 2009-11-30 |  | Migration of former SIS addresses Joe Lampo raised concerns in regard to addresses and other changes from Plus being overridden (7/25/2009). Need to research 'who wins' in the gpsync process and the impact of a record change that is coming over 'older' than the effective date in Banner. The legacy conversion (COBOL) programs must be critiqued to determine date timestamping, logic behind "who wins" and the dates being insert into the Banner/Oracle tables. (Update 7/28/2009) | Joe Lampo (Jim and Jerrick)
Student | Medium |  | 2009-11-30 |  | Interface with Etudes solution (Distance Learning) | Chien Shih
Student | Medium |  | 2009-11-30 |  | Test score legacy system – integration with Banner | Jerrick and Dottie Marron
Student | Medium |  | 2009-11-30 |  | ECMS course-management interface | Chien Shih
Overall | Medium |  | 2010-05-01 |  | Load of historical records into ODS Enterprise Reporting Team to determine data to be converted into ODS (and not the Banner transactional system). (Update 7/26/2009) | EIS Team with input from Core Team
Finance | Medium |  |  |  | Integration with Augusoft "learning management" system connections for Finance-record reporting
General | Medium |  |  |  | Unnecessary SPRTELE entries by GP Synch | Linda will coordinate with Jim and Joe
Luminis | Medium |  |  |  | SSO to products like HR’s Liquid Office | Kurt Hueg
Luminis | Medium |  |  |  | Use of Fin Aid channels, including access to PDF files to be printed as input documents by students | Cindy with Luminis team
Luminis | Medium |  |  |  | Use of Finance channels | Hector with Luminis team
Luminis | Medium |  |  |  | Automatic account creation from Banner | Matt working with Bill Baldwin
ODS | Medium |  |  |  | SSR implementation (Self-Service Reporting) | Bob Barr to recommend/Chien Shih Decision
ODS | Medium | 2009-06-17 |  |  | Finance security--Detail sent to Linda Wooden on security model/pass thru from Banner-->ODS. Status of the review of that material is required. | Bob Barr/Security Team
ODS | Medium |  |  |  | ODS Administrator needed | Vicki now covering
Overall | Medium |  |  |  | AppWorx implementation | Tom coordinating – holding until Finance testing in 8 environment
Overall | Medium |  |  |  | Common matching rules for vendors | Linda to test in PPRD
Overall | Medium |  |  |  | Banner printers – default to specific printer when printing from GJIREVO | Tom Roza
Finance | Low |  |  |  | Integration with Escape system used for Stores Inventory
Integration | Low |  |  |  | Moodle and Etudes integration | Planning Stage
Overall | Low |  |  |  | D270 printer | Chien Shih
Overall | Low |  |  |  | ePrint use | Joe Lampo
Finance | Closed |  | 2009-06-30 | June | Approval queues for technical purchases – special exemptions designed | Hector Quinonez
ODS | Closed | 2009-07-09 | 2009-07-13 | 2009-07-15 | Cancellation/rescheduling of ODS Human Resources Training week of 8/3/2009 Rescheduled to the week of 8/24/2009. (Updated 7/26/2009) | Bob Barr, Kim Chief Elk, Chien Shih (Deb Treacy schedule).
BDMS | Closed | 2009-07-14 | 2009-07-16 | 2009-07-14 | Schedule preliminary discussion with SunGard Higher Education Resource--environment requirements, recommendations, implementation strategy | Scheduled; call occurred 7/24/2009 (Chien Shih, Deb Treacy, Louis Chen)
Technical | Closed | 2009-07-13 | 2009-07-20 | 2009-07-16 | Deactivating of PR addresses affecting Direct Deposits (process developed by Dominic Martinez) | Joe Lampo, Linda Wooden
Luminis | Closed | 2009-06-29 | 2009-07-23 | 2009-07-31 | MAC SSO issues--Luminis upgrade to occur during the week of 7/13/2009. Matt R. has opened SR# 1-384249021 with the CSC. (Update 7/26/2009) Update 7/30/2009 Matt R. continues to work with Customer Support Center. Next step is to replicate in test environment. | Matt; Tom (monitoring)
Overall | Closed |  | 2009-07-23 | 2009-07-29 | Creation of a CONV8 instance | Tom Roza
Fin Aid | Closed | 2009-07-20 | 2009-07-24 | 2009-07-22 | Resolution of scheduling conflicts--ODS, Milestone Review, Training Week of 9/14 | Deb Treacy
HR | Closed | 2009-07-20 | 2009-07-24 | 2009-07-29 | Rescheduling, Postponement, Cancellation of HR End User Training Needs Assessment--Postponed to March 2010 | Kim Chief Elk, Chien Shih
ODS | Closed | 2009-07-20 | 2009-07-24 | 2009-07-22 | Resolution of Student and Financial Aid ODS Reporting Sessions | Deb Treacy
Finance | Closed |  | 2009-07-29 | 2009-07-29 | Schedule technical assistance for resolving address issues caused by gpsync (attempting to schedule (Update 7/27/2009))--will analyze using internal talents. Look at COBOL extracts and CTOOL customizations (e.g. dates); analyze "who wins" | Deb Treacy
Finance | Closed | 2009-07-29 | 2009-07-30 | 2009-07-30 | Raised by Fred Sherman Maas employees were not trained in use of Banner Finance. Employees have attended training; however, if follow-up training must occur contact Hector. | Deb Treacy; Chien Shih
Luminis | Closed | 2009-07-02 | 2009-07-30 | 2009-07-16 | Temporary Test/Development Environment while Carlsbad site comes online (coordinate effor 7/13/2009--final schedule discussion) | Tom (Deb Treacy scheduling)
BDMS | Closed | 7/24/20090 | 2009-07-31 | 2009-07-29 | Schedule BDMS activities for Finance deployment | Deb Treacy with input from Chien Shih
General | Closed | 2009-07-30 | 2009-07-31 | 7/31/20009 | Data Extract with Key Functionality is required within INB. This is functionality is valuable for all areas. (Requested by Fin Aid.) | Deb Treacy
Finance | Closed |  |  | June | Vendor aliases not moved from TEST to PROD
Finance | Closed |  |  | June | Direct-deposit use in PROD
Finance | Closed |  |  | June | Maintenance of student-refund direct deposit records
Finance | Closed |  |  | July | Flint Theatre interface with Banner Finance | New software will comply with District policies
General | Closed |  |  | June | Source/Institutional table conversion – major effort by Lourdes
General | Closed |  |  | July | Messages from GP Synch process Being rewritten to simplify analysis/following. | Jim Clow
HR | Closed |  |  | June | Salary Planner install
Luminis | Closed |  |  | 2009-07-16 | GCF training--coordinating requirement for training with Chien Shih Scheduled week of 8/3/2009. (Updated 7/26/2009) | Deb Treacy Researched--Chien Shih to approve.
Student | Closed |  |  | June | Conversion of admissions/recruiting data
Overall | Closed |  |  | June | CalB 8 install, including BOG menus
Overall | Closed |  |  | June | Security-class access by users not going through Finance training (SSB users)
Overall | Closed |  |  | June | Decision on BLDG and RDEF structures