EIS Steering Committee

October 14, 2009 Meeting Notes

Attendees: Fred Sherman, Chien Shih, Andy Dunn, Sherri Mines, Kim Chief Elk, Peggy Davis from SunGard, Carmen Redmond and Kari Elliott (note taker).

- Telecommuting Policy Procedure (Banner EIS only):

- Approved by Chancellor Staff already.

- Will present to Core Committee Monday, October 19th for approval.

- Telecommuting is for after work hours – overtime.

- No remote access to old Admin System.

- Approved by the Steering Committee.

- Review of Draft Message for On line Time Entry (Student Employee &Temp Employee:

- 250 to train on process (approvers mainly)

- Training to be scheduled in November.

- New electronic process for hiring temp employees.

- Draft approved by Steering Committee.

- Issues Report:

- Banner Finance.

- Provided additional training for approximately 30 users.

- Still have openings for the October 23rd training session.

- Approval queus turned on October 15th per Hector Quinonez.

- November 19th – 22nd will be the conversion to Banner Finance 8.0 from Banner Finance 7.4.

- Banner HR/Payroll.

- Go Live readiness briefing October 15th.

- Issues resolved by November 1st; Chien is confident issues will be resolved.

- Test Environment set up November 1st – 8th.

- Refresher training (job function related) November 9th.

- Kick off training November 17th; will send memo out.

- Progress Report Presented:

- Major tasks achieved:

- October 2, 2009 – Complete HR/Payroll Issues resolution.

- Budget lapsing is still being worked out.

- Step increase is still being worked out.

- October 2, 2009 – Luminis requirements definition for HR and Student.

- Channels are defined.

- November 9th – platform set-up; identify users and define security.

- October 6, 2009 – CCCApply Implementation Kick Off.

- October 9, 2009 – Complete HR/Student Faculty Load Demo.

- October 8, 2009 – 3CBG Conference; 50+ FHDA users attended.

- October 12, 2009 – Academic History Conversion starts.

- October 18, 2009 – 2nd mid month Payroll/Direct Deposit testing.

- Milestones Ahead:

- October 30, 2009 – ECMS/C3MS integration testing.

- Exchange data through interface between Banner and Curriculum Management Systems.

- November 5, 2009 – 3rd monthly Payroll parallel testing/ Direct deposit testing.

- November 9, 2009 – HR/Payroll refresh training.

- November 16, 2009 – Mock admission test (Student).

- November 17, 2009 – HR/Payroll Campus training on Time Entry.

- November 20, 2009 – Go Live Readiness Review (HR/Payroll).

- November 20, 2009 – CCCApply in beta test.

- Beta environment ready for sending mock student application.

- November 30, 2009 – 1st Mock Registration (Student).

- Project progression is on track.

- Project still in budget. Remaining implementation hours are enough to finish modules.