EIS Steering Committee

November 11, 2009 Meeting Notes

Attendees: Fred Sherman, Chien Shih, Andy Dunn, Sherri Mines, Letha Jeanpierre, Carmen Redmond and Kari Elliott (note taker).

- Telecommuting Policy Procedure (Banner EIS only):

- Has been implemented as District policy.

- Review of Draft Message for On line Time Entry (Student Employee &Temp Employee):

- Presented final copy; locations have been filled in for training dates.

- Will be sent to supervisors through Financial Aid.

- Issues Report:

- Banner Finance.

- Convert Finance 7.4 to 8.3 November 19-23.

- Mock conversion completed November 6 and has been turned over to Hector Quinonez for testing. Hector will notify his staff November 12, 2009.

- If conversion is unsuccessful, conversion can be done again Thanksgiving weekend.

- Banner HR/Payroll.

- Go Live Assessment by independent consultant scheduled for November 18-20.

- On target for Go Live January.

- Progress Report Presented:

- Major tasks achieved in October:

- 2nd parallel payroll completed October 1, 2009.

- Test of leave hours.

- Fewer errors than previous parallel payroll.

- October 1, 2009 - Luminis channel set up within Banner for HR & Student access.

- October 6, 2009 - CCCApply installed and ready for mock registration testing November 30, 2009.

- October 30, 2009 – ECMS/C3MS testing starts; course management system interface.

- Milestones Ahead in November:

- November 5-12 – 3rd parallel payroll testing.

- November 9-11 – CCCApply technical training.

- November 17-19 – HR/Payroll Sprint Session.

- November 18-20 – Independent assessment of HR/Payroll Go Live readiness; assessment report will be published.

- November 19-23 – Finance Module conversion from 7.4 to 8.3.

- November 17-19 – Enterprise Data Warehouse (EDW) training.

- November 30 – 1st mock registration using CCCApply and Student module.

- November 30 – Student employment Self Service Time Entry training; 2 sessions, 9am-12pm in the Toyon Room and 1pm-4pm in the Altos room on Foothill campus.

- December 1- Student employment Self Service Time entry training; 2 sessions, 9am-12pm in Adm 109 and 1pm-4pm in LCW 16 on De Anza Campus.

- Project progression is on track.

- Project still in budget. Remaining implementation hours are enough to finish modules.

- Banner will no longer interface with payment gateways. A decision needs to be made regarding which 3rd party payment gateway to use. It will be an on-going cost and new money needs to be identified. The decision needs to be made before July 1, 2010.