EIS Steering Committee

April 21, 2010 Meeting Notes

Attendees: Fred Sherman, Chien Shih, Andy Dunn, Sherri Mines, Rose Myers and Kari Elliott (note taker).

- Review Highlights:

- Labor distribution and budget encumbrance liquidation is up to date.

- Finance March month end closed successfully.

- Financial Aid disbursement/Higher One project kick off – April 20, 2010.

- Chien Shih is working with Hector Quinonez on post modifiers.

- Instructional Support Go Live – April 23, 2010.

- Student to begin testing – April 23, 2010.

- Touchnet Payment Gateway ready for testing end of April and is PCI compliant.

- Student Load Testing – Beginning of May.

- Faculty training scheduled to begin week of May 17, 2010; still finalizing training schedule.

- Student Team will go live with Summer Counseling 100 – May 22, 2010.

- Chien Shih will begin meeting with the Teams next week to discuss ARGOS reporting. Student & Instructional Support will be the first teams Chien will be meeting.

- Major Tasks Achieved – March/April:

- Held various Student Summits throughout March.

- Instructional Support ready for pre-production testing of Summer Catalog & Schedule – April 1, 2010.

- First 2 scheduled testing completed.

- Instructional Support – Summer Catalog & Summer Schedule Go Live – April 23, 2010.

- Major Tasks Ahead – April/May:

- Academic History Conversion completed – April 23, 2010.

- Records converted from year 2000.

- Ready for testing.

- Student migrate to Pre-Production – May 7, 2010.

- Begin final testing.

- Faculty training begins – May 17, 2010.

- Student Counseling 100 Go Live – May 22, 2010.

- Summer student registration – June 1, 2010.

- Project Budget:

- 673.50 consulting hours remaining.

- 321 consulting hours reduced from Project Management.

- 971.50 consulting hours needed; propose moving $250,000.00 from contingency fund to supplement. Will still have a million in the contingency fund.

- Other Issues:

- Interface between Payroll and Finance.

- STRS/PERS – California Solution Center for SunGard is working on the problem. It is a problem that affects all California schools. Should be resolved by May 2, 1010.

- Labor Distribution

- Corrected through March 2010.

- Liquidate encumbrances through March 2010.

- Resolved for April.

- Temporary Cash Account.

- Chien Shih is working with Hector Quinonez to resolve.