EIS Steering Committee

May 19, 2010 Meeting Notes

Attendees: Fred Sherman, Chien Shih, Sherri Mines, Letha Jeanpierre and Kari Elliott (note taker).

- Review Highlights:

- Finance successfully closed April.

- Still working out the temp cash accounts clearing out.

- Financial Aid successfully processed 10,826 students on line.

- 7,000 De Anza students.

- 2,000 Foothill students.

- 1000 concurrent students.

- Student Load test scheduled for May 19, 2010 at 5:00pm.

- Will test 10,000 concurrent students.

- Additional testing scheduled for July.

- May 22, 2010 Student Go Live with Counseling 100

- Confident will be successful.

- May 27, 2010 Foothill EOPS/Special student Summer registration goes live.

- June 1, 2010 Foothill general student Summer Registration goes live; De Anza EOPS go live.

- June 3, 2010 De Anza Summer general student go live.

- Fall registration begins August 1, 2010.

- Major Tasks Achieved – May/June:

- Student team moves to TRN8; final testing of catalog & schedule – April 23, 2010.

- Date to register script – Delayed until May 20, 2010 because of system testing.

- Student migrates to pre-production – May 18, 2010.

- Faculty training delayed until May 26, 2010.

- Announcement went out to Summer faculty – May 13, 2010

- Training material ready May 22, 2010.

- It was brought up in Chancellor Staff meeting to add more training sessions and open to all faculty.

- Will propose to Faculty Training team at next meeting – May 24, 2010.

- Academic History Conversion completed and ready for testing – May 16, 2010.

- Moved history from 2000 forward; student side only.

- Accounts Receivable/Payment Gateway testing begins – May 18, 2010.

- Luminis Production final testing – on going.

- Major Tasks Ahead – May/June:

- Move Legacy system Accounts Receivable balance forward to Banner – June 1, 2010.

- May move earlier; meeting later this week to discuss with Hector Quinonez and campus cashiers.

- De Anza student Summer registration for EOPS/special programs – June 1, 2010.

- De Anza general student Summer registration – June 3, 2010.

- Banner training for Summer Faculty – May26, 2010 – June 10, 2010.

- Faculty contract for Summer on line – May 27, 2010.

- Faculty contract signed – June 11, 2010.

- Fall instructional support catalog & schedule move to TRN8 for testing – June 4, 2010.

- Project Budget:

- Still on target.