EIS Steering Committee

August 26, 2009 Meeting Notes

Attendees: Fred Sherman, Chien Shih, Andy Dunn, Carmen Redmond, Sherri Mines, Rose Myers, Kim Chief Elk, Debra Treacy from SunGard and Kari Elliott (note taker).

- Report results from Mini Summit, August 5th-6th:

- Summit was to Kick-Off HR/Payroll & Student go live.

- Project calendar with milestones created.

- Discussed major issues and resolved them.

- Progress Report Presented:

- Major tasks achieved:

- BDMS Kick-Off – August 10th; in production October 21, 2009.

- Finance Self Service training completed August 6, 2009.

- Still need additional training; not all staff was trained and those who were trained early need refresher training.

- Chien Shih is working on an on-going training plan and will present to the Committee when ready.

- Banner resolution proposal delivered August 17, 2009, regarding Banner HR key issue 10/12 month for part time faculty; currently under review.

- Milestones Ahead:

- September 1, 2009 – First Parallel check run.

- January 12, 2010 – First mid month payroll in production.

- January 29, 2010 – First end of month payroll in production.

- Catalog converted; schedule to conversion to be done by August 31, 2009.

- Determine Academic History conversion (1983-2007)

- Duplicate ID clean up.

- Complete by October 12, 2009.

- CCCApply contract finalized; Chien Shih will arrange a meeting with both colleges to discuss impact.

- CCCApply in production March 1, 2010.

- Student Self Service Go Live – May 11-18, 2010.

- Project progression is on track.

- Project Budget:

- The question was raised if enough money has been set aside for training; there is enough for implementation training, not additional training.

- Chien Shih will report to the Committee the results of mini summit (held August 26, 2009) regarding additional training and training implementation solutions.