EIS Steering Committee

September 23, 2009 Meeting Notes

Attendees: Fred Sherman, Chien Shih, Andy Dunn, Sherri Mines, Rose Myers, Kim Chief Elk, Debra Treacy from SunGard and Kari Elliott (note taker).

- Additional SSB training for Finance Module for 50 users:

- September 28th at Foothill, September 29th at De Anza.

- October 5th at De Anza, October 23 at Foothill.

- Instructor led training in the morning and open lab in the afternoon.

- Sent email to the VPs and Vice Chancellors of both colleges regarding training.

- In process of buying self service training CDs from SunGard.

- Approval ques turned on October 15th:

- Need to scynchronize both colleges.

- De Anza validated.

- Foothill – still validating.

- Banner HR/Payroll Status:

- Many differences between old system and Banner.

- 45 issues have been identified and need to be addressed and resolved quickly.

- Staff impact: heavy workloads, may have to adjust staffing levels.

- Progress Report Presented:

- Major tasks achieved:

- September 1, 2009 – HR first parallel payroll run.

- September 1, 2009 – CCCApply contract ready for signature.

- September 3, 2009 – Conversion of Catalogue and Schedule from IAplus to Banner (Summer and Fall quarter).

- September 11, 2009 – HR readiness review; first assessment for Go Live readiness for January 1, 2010.

- September 17, 2009 – Mid month payroll parallel run.

- September 22, 2009 – Production data replication to DR site; live data replication established for finance module to Carlsbad, CA, Disaster Recovery site.

- Milestones Ahead:

- October 1, 2009 – HR/Payroll 2nd parallel payroll run.

- October 6, 2009 – CCCApply implementation kick off.

- October 8, 2009 – 3CBG Conference; 50+ attendees from FHDA.

- October 12, 2009 – Academic History conversion starts.

- October 18, 2009 – 2nd mid-month payroll/Direct deposit testing.

- October 30, 2009 – ECMS/C3MS integration testing starts.

- Project progression is on track.

- Project still in budget. Remaining implementation hours are enough to finish modules.