| EIS Project event schedule 2007 |  |  |  |  |
| --- | --- | --- | --- | --- |
| Date | Event description | Participants/Responsibility | Location | Status |
| 3/13 | Project kick off | All team members | Board Room | Done |
| 3/14 | Decision Director tool training | All team members | KCI and De Anza | Done |
| 3/14 | Brain Storming Forum Opening | All team members |  | Done |
| 3/29 | Review of Business Process Knowledge Pack | Functional Sponsor/Leads |  | Done |
| 4/13 | Finalize Business Process Knowledge Pack | Functional Sponsor |  |  |
| 4/12 | Business Review Process Planning sessions with Dan Miller/ Advantiv | Functional Sponsor/Team Leads | Adm109 |  |
| 4/13 | Business Process Review planning sessions with Dan Miller/ Advantiv | Functional Sponsor/Team Leads | Board Room |  |
| 4/13 | Begin Review of Functional Requirements Knowledge Pack | Functional Sponsor |  |  |
| 4/13 | Close of Brain Storming Forum | ETS/Advantiv |  |  |
| 4/16 | Business Process Review Forum Opening | ETS/Advantiv |  |  |
| 4/16 | Forum Training 9-noon | All | TBA |  |
| 4/17 | Forum training 1-5 p.m. | All | TBA |  |
| 4/27 | Finalize Functional Requirements Knowledge Pack | Functional Sponsor |  |  |
| 4/30 | Close of Business Process Review Forum | ETS/Advantiv |  |  |
| 5/3 | Functional Requirements Gathering planning sessions with Dan Miller/ Advantiv | Functional Sponsor/Team Leads | Plant D160 |  |
| 5/4 | Functional Requirements Gathering planning sessions with Dan Miller/ Advantiv | Functional Sponsor/Team Leads | Adm109 |  |
| 5/7 | Functional Requirements Gathering Forum Opening | ETS/Advantiv |  |  |
| 5/7 | Forum training 9-noon | All | TBA |  |
| 5/8 | Forum training l-5 p.m. | All | TBA |  |
| 5/31 | Close of Functional Requirements Gathering Forum | ETS/Advantiv |  |  |
| 6/2 | Validation of Functional Requirements | Functional Sponsor/Steering Committee |  |  |
| 6/6 | Finalize the functional requirements | Steering Committee |  |  |
| 6/11 | 1st ITB Process review | Dan Miller/Purchasing/Functional sponsor |  |  |
| 6/18 | 2nd ITB Process review | Purchasing/ETS |  |  |
| 6/25 | 3rd ITB Process review | Purchasing/ETS |  |  |
| 7/2 | Final ITB Process review | Dan Miller/Steering Committee/Purchasing |  |  |
| 7/9 | Release of ITB | Purchasing |  |  |
| 8/30 | Deadline for ITB Submission | Purchasing |  |  |
| 8/31 | Begin review of ITB | Functional Sponsor/Steering Committee |  |  |
| 9/26 | Vendor Day invitation | ETS/Functional Sponsor |  |  |
| 9/27 | Vendor Day invitation | ETS/Functional Sponsor |  |  |
| 9/28 | Vendor Day invitation | ETS/Functional Sponsor |  |  |
| 10/1 | Conduct vendor demo | ETS |  |  |
| 11/15 | Release final report and decision | ETS/Purchasing |  |  |
| 12/31 | Complete contract negotiation | ETS/Purchasing |  |  |

Revised 
April 1, 2007