| EIS Project Event Schedule 2007 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Date | Event description | Participants/Responsibility | Location |  | Status |
| 3/13 | Project kick off | All team members | Board Room |  | Done |
| 3/14 | Decision Director tool training | All team members | KCI and De Anza |  | Done |
| 3/14 | Brain Storming Forum Opening | All team members |  |  | Done |
| 3/29 | Review of Business Process Knowledge Pack | Functional Sponsor/Leads |  |  | Done |
| 4/13 | Finalize Business Process Knowledge Pack | Functional Sponsor |  |  | Done |
| 4/12 | Business Review Process Planning sessions with Dan Miller/ Advantiv | Functional Sponsor/Team Leads | Adm109 |  | Done |
| 4/13 | Business Process Review planning sessions with Dan Miller/ Advantiv | Functional Sponsor/Team Leads | Board Room |  | Done |
| 4/13 | Begin Review of Functional Requirements Knowledge Pack | Functional Sponsor |  |  | Done |
| 4/13 | Finalize Student Forum Questions | Student Advisors |  |  | Done |
| 4/17 | Business Process Review Forum Opening | ETS/Advantiv |  |  | Done |
| 4/16 | Forum Training Noon -5 p.m. | All | KCI 4008 |  | Cancel |
| 4/17 | Forum training 9 - noon | All |  |  | Cancel |
| 4/17 | Functional KP distributed | Teams |  |  | Done |
| 4/20 | Close of Brain Storming Forum | ETS/Advantiv |  |  | Done |
| 4/23 | BPR Forum Training 1-2:30 | All | KCI4008 |  | Done |
| 4/24 | BRP Forum Training 11-2 | All | SCS Conf |  | Done |
| 5/1 | Bid Document Details to Purchasing | Chien |  |  |  |
| 5/3 | Functional Requirements Gathering planning sessions with Dan Miller/ Advantiv | Functional Sponsor/Team Leads | Plant D160 |  | Done |
| 5/4 | Functional Requirements Gathering planning sessions with Dan Miller/ Advantiv | Functional Sponsor/Team Leads | Adm109 |  | Done |
| 5/7 | Forum training Noon -5 | All | KCI 4008 |  | Done |
| 5/8 | Forum training 10 - noon | All | LCW Trng Lab |  | Done |
| 5/8 | Finalize Student Survey | Advantiv, Kathy |  |  |  |
| 5/8 | Close Business Process Review Voting Forum | ETS/Advantiv |  |  | Done |
| 5/11 | Finalize Functional Requirement KP | Sponsors/Advantiv |  |  | Done |
| 5/20 | Open Functional Requirements Forum | ETS/Advantiv |  |  | Done |
| 6/8 | Student Forum Opens | Students- Tentative |  |  |  |
| 6/8 | Bid doc w/Advantiv DD draft complete | Purchasing/ETS |  |  | Done |
| 6/15 | Close Functional Requirements Voting Forum | ETS/Advantiv |  |  | Done |
| 6/18- 6/21 | Validation of Functional Requirements Begins with Dan Miller 6/18 9:00-10:30 Board Room Individual appts 6/18-21 | Functional Sponsor/Steering Committee |  |  | Done |
| 6/18 | 2nd RFP Process review | Purchasing/ETS |  |  |  |
| 6/21 | Finalize the functional requirements | Teams |  |  | Done |
| 6/25 Wk | 1st Review of bid documents | Carmen/Chien |  |  | Done |
| 7/9 | Board approval of RFP procedures/criteria | Fred |  |  | Done |
| 7/10 | Begin Demo Scenario Development | Teams |  |  | Done |
| 7/10 | Draft RFP to consultant | ETS |  |  | Done |
| 7/13 | Final RFP Draft complete | Carmen/Chien |  |  |  |
| 7/20 | Draft RFP review by consultant complete | ETS |  |  | Done |
| 8/3 | Final changes to RFP to Purchasing | Chien |  |  | Done |
| 8/1 | Ad to SJ Post Record | Purchasing |  |  | Done |
| 8/7 | Advertise dates 8/7 and 8/14 | Purchasing |  |  | Done |
| 8/7 | RFP post on BidNet and email doc to vendors | Purchasing |  |  | Done |
| 8/14 | Advantiv online bid opens | Advantiv |  |  | Done |
| 9/7 | Finalize Demo scenarios for distribution to vendors | Teams |  |  | Done |
| 8/31 | Deadline for RFP written questions from bidders | Purchasing |  |  | Done |
| 8/22 | Pre-bid conference Wed Aug 22 TBA | Purchasing |  |  | Done |
| 9/10 | Issue bid amendments, if necessary | Purchasing |  |  | Done |
| 9/26 | Last date/time to enter DD responses and print out hard copy. Open sealed bids 2:00 p.m. |  |  |  | Done |
| 9/26 | Begin review of bid responses |  |  |  | Done |
| 10/22-26 | Vendor Demonstration – Sungard Banner- | Team |  |  | Done |
| 10/29-11/2 | Vendor Demonstration- Datatel | Team |  |  | Done |
| 11/7 | Site Visit – San Mateo CCD (Sungard) | Team |  |  |  |
| 11/17 | Site Visit – Contra Costa CCD (Datatel | Team |  |  |  |
| 11/16-30 | Best and final offer |  |  |  |  |
| TBA | Draft board submittal | ETS/Purchasing |  |  |  |
| 11/21 | Notification to bidders | Purchasing |  |  |  |
| 12/14 | Board submittal deadline | Purchasing/ETS |  |  |  |
| 1/7/08 | Board Meeting - | ETS/Purchasing |  |  |  |
| TBA | Complete contract negotiation | ETS/Purchasing |  |  |  |

Revised October 31, 2007