## Summary Waterfall
Major Activity | Major Phase | Major Milestone | Start Date | Finish Date | 2008 PTD | Oct | Nov | Dec | 2009 Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | 2010 Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | 2011 Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Software Installation |  | Oracle, Banner and Luminis Installed on FHDA hardware; Knowledge Transferred to FHDA IT Organization on Configuration and Operations | 2008-07-21 | 2008-12-05
Software Installation | Installation Preparation | Pre-Install Checklist Verified | 2008-09-22 | 2008-09-26
Software Installation | Conduct Installation | Oracle, Banner and Luminis Installed on FHDA hardware | 2008-10-01 | 2008-11-25
Software Installation | Oracle/Banner Installation Review | Knowledge Transferred to FHDA IT Organization on Configuration and Operations | 2008-10-22 | 2008-12-05
Software Installation | Luminis Platform Installation Review | Knowledge Transferred to FHDA IT Organization on Configuration and Operations | 2008-07-21 | 2008-12-05
Business Process Analysis |  | Selected Business Processes Analyzed and Documented | 2008-09-15 | 2008-12-29
Business Process Analysis | BPA Planning | Agendas for BPA On-site Reviewed | 2008-09-15 | 2008-10-06
Business Process Analysis | BPA On-site Analysis | On-site BPA Analysis Conducted | 2008-10-20 | 2008-12-12
Business Process Analysis | BPA Write-up, Follow-up, and Document Preparation | Future State Process Models and Recommendations Document Delivered and Reviewed | 2008-10-27 | 2008-12-29
Identity and Access Management |  | Identity Management Solution Deployed in Production | 2008-10-13 | 2009-06-17 | bar: Feb to Jun
Identity and Access Management | Assessment | Identity Management Strategy in Place | 2008-10-13 | 2008-11-21
Identity and Access Management | Planning | Detailed Plans, Specifications for IAM Implementation Developed and Reviewed | 2009-01-16 | 2009-02-27
Identity and Access Management | Baseline Solution Implementation | Baseline Identity Management Code Developed and Tested | 2008-12-15 | 2009-02-27 | bar: Feb
Identity and Access Management | Baseline Solution Deployment | Baseline Identity Management Solution Deployed in Production | 2009-03-09 | 2009-06-17 | bar: Mar to Jun
Identity and Access Management | Enhanced Solution Implementation | Enhanced Identity Management Code Developed and Tested | 2009-08-03 | 2009-09-04 | bar: Aug to Sep
Identity and Access Management | Enhanced Solution Deployment | Enhanced Identity Management Solution Deployed in Production | 2009-09-07 | 2009-11-06 | bar: Sep to Nov
Integration/Interfaces |  | Integration and Interfaces Deployed in Production | 2008-10-06 | 2011-01-31
Integration/Interfaces | Integration Assessment | Integration Assessment Document Delivered | 2008-10-06 | 2008-12-05
Luminis IV Platform Phase 1 - Finance Users |  | Luminis Platform Deployed in Production | 2008-09-03 | 2009-07-02 | bar: Feb to Jul
Luminis IV Platform Phase 1 - Finance Users | Assessment | TPW Delivered, Project Definition Document Delivered | 2008-09-22 | 2008-10-15
Luminis IV Platform Phase 1 - Finance Users | Planning | Organizational and Content Planning Completed | 2008-11-17 | 2008-12-15
Luminis IV Platform Phase 1 - Finance Users | Implementation | Test Environment Installed | 2008-10-15 | 2008-12-05
Luminis IV Platform Phase 1 - Finance Users | Implementation | System Education, CAT Training Completed | 2008-11-03 | 2009-02-19 | bar: Feb
Luminis IV Platform Phase 1 - Finance Users | Implementation | Production Environment Installed | 2009-02-23 | 2009-04-08 | bar: Feb to Apr
Luminis IV Platform Phase 1 - Finance Users | Implementation | Luminis Platform Certified | 2009-05-25 | 2009-06-26 | bar: May to Jun
Luminis IV Platform Phase 1 - Finance Users | Implementation | Technical and Operational Readiness Validated | 2009-06-29 | 2009-07-02 | bar: Jun to Jul
Luminis IV Platform Phase 2 - HR Users | Implementation | Organization Readied and Content to be Provided to HR Users Completed | 2009-08-03 | 2010-01-01 | bar: Sep to Dec
Luminis IV Platform Phase 3 - Student Users | Implementation | Organization Readied and Content to be Provided to Student Users Completed | 2009-09-01 | 2010-02-15 | bar: Oct to Dec
Luminis IV Platform Phase 1 - Finance Users | Close-out | Lessons Learned and Transition to Maintenance Strategy | 2009-07-05 | 2009-07-09 | bar: Aug
Banner Finance Phase 1 - General Accounting |  | Banner Finance Module (General Accounting) Deployed in Production | 2008-10-10 | 2009-07-01 | bar: Feb to Jul
Banner Finance Phase 1 - General Accounting | System Education | System Education completed; staff readied for subsequent implementation activities | 2008-10-27 | 2008-05-15 | bar: Feb to May
Banner Finance Phase 1 - General Accounting | Prototype Configuration and Testing | Completed Chart of Accounts, Validated Accounting Process | 2008-10-27 | 2009-02-20 | bar: Feb
Banner Finance Phase 1 - General Accounting | Prototype Configuration and Testing | Banner Finance data base populated sufficiently to support ODS report development | 2009-02-20 | 2009-03-15 | bar: Feb to Mar
Banner Finance Phase 1 - General Accounting | Prototype Configuration and Testing | Banner 8 Migration Plan Completed | 2009-03-01 | 2009-03-15 | bar: Mar
Banner Finance Phase 1 - General Accounting | Prototype Configuration and Testing | Banner 8 Issues Resolves | 2009-03-18 | 2009-04-15 | bar: Mar to Apr
Banner Finance Phase 1 - General Accounting | Data Migration | Balance, Budget Loaded; Vendors Entered | 2009-04-18 | 2009-04-27 | bar: Apr
Banner Finance Phase 1 - General Accounting | Production Simulation Testing | Parralel 1 Day Validated Month End Run Validated | 2009-05-01 | 2009-05-14 | bar: May
Banner Finance Phase 1 - General Accounting | Information Access | All queries and reports required for Production tested and deployed | 2009-03-01 | 2009-06-12 | bar: Mar to Jun
Banner Finance Phase 1 - General Accounting | System Integration Development and Testing | Integration/Interfaces Deployed in Production | 2009-02-16 | 2009-06-12 | bar: Feb to Jun
Banner Finance Phase 1 - General Accounting | End User Training & Rollout | Necessary End Users Certified; Procedure Manuals Signed Off and Ready for Production Use | 2009-02-16 | 2009-06-12 | bar: May to Jun
Banner Finance Phase 1 - General Accounting | System Deployment and Maintenance | FHDA Organization, Maintenance Approach Readied and in Place; Plans in Place for Resolving Post-Go Live Issues | 2009-05-25 | 2009-07-10 | bar: May to Jul
Banner Finance Phase 2 - Budget |  | Banner Finance Module (Budget) Deployed in Production | 2009-08-17 | 2010-02-01 | bar: Aug to Dec
Banner Finance Phase 2 - Budget | System Education | System Education completed; staff readied for subsequent implementation activities | 2009-08-17 | 2009-08-21 | bar: Aug
Banner Finance Phase 2 - Budget | Prototype Configuration and Testing | Prototype Configured and Readied for subsequent testing and deployment activities | 2009-08-17 | 2009-10-30 | bar: Aug to Oct
Banner Finance Phase 2 - Budget | Data Migration | All required data converted into Production | 2009-08-17 | 2009-10-30 | bar: Aug to Oct
Banner Finance Phase 2 - Budget | Information Access | All queries and reports required for Production tested and deployed | 2009-08-17 | 2009-12-04 | bar: Aug to Dec
Banner Finance Phase 2 - Budget | System Integration Development and Testing | Integration/Interfaces Deployed in Production | 2009-08-17 | 2009-12-04 | bar: Aug to Dec
Banner Finance Phase 2 - Budget | Production Simulation Testing | Production Simulation Testing Signed Off; Module Readied for Production | 2009-10-05 | 2009-12-18 | bar: Oct to Dec
Banner Finance Phase 2 - Budget | End User Training & Rollout | Necessary End Users Certified; Procedure Manuals Signed Off and Ready for Production Use | 2009-10-05 | 2009-12-18
Banner Finance Phase 2 - Budget | System Deployment and Maintenance | FHDA Organization, Maintenance Approach Readied and in Place; Plans in Place for Resolving Post-Go Live Issues | 2010-01-04 | 2010-02-12
Banner Human Resources |  | Banner Human Resources Module Deployed in Production | 2008-10-21 | 2010-01-04
Banner Human Resources | System Education | System Education completed; staff readied for subsequent implementation activities | 2008-11-10 | 2009-08-14 | bar: Feb to Aug
Banner Human Resources | Prototype Configuration and Testing | Prototype Configured and Readied for subsequent testing and deployment activities | 2008-11-10 | 2009-10-02 | bar: Feb to Oct
Banner Human Resources | Information Access | All queries and reports required for Production tested and deployed | 2008-11-10 | 2009-11-27
Banner Human Resources | Data Migration | All required data converted into Production | 2009-03-23 | 2009-11-27 | bar: Mar to Nov
Banner Human Resources | System Integration Development and Testing | Integration/Interfaces Deployed in Production | 2009-03-23 | 2010-01-04
Banner Human Resources | Production Simulation Testing | Production Simulation Testing Signed Off; Module Readied for Production | 2009-08-10 | 2009-11-17 | bar: Aug to Nov
Banner Human Resources | End User Training & Rollout | Necessary End Users Certified; Procedure Manuals Signed Off and Ready for Production Use | 2009-08-10 | 2009-12-18 | bar: Aug to Dec
Banner Human Resources | System Deployment and Maintenance | FHDA Organization, Maintenance Approach Readied and in Place; Plans in Place for Resolving Post-Go Live Issues | 2009-11-16 | 2010-01-15 | bar: Nov to Dec
Banner Student - Admissions |  | Banner Student Module (Admissions) Deployed in Production | 2008-10-06 | 2010-02-15
Banner Student - Admissions | System Education | System Education completed; staff readied for subsequent implementation activities | 2009-01-19 | 2009-09-04 | bar: Feb to Sep
Banner Student - Admissions | Prototype Configuration and Testing | Prototype Configured and Readied for subsequent testing and deployment activities | 2009-01-19 | 2009-10-16 | bar: Feb to Oct
Banner Student - Admissions | Data Migration | All required data converted into Production | 2009-01-19 | 2009-02-15
Banner Student - Admissions | Information Access | All queries and reports required for Production tested and deployed | 2009-01-19 | 2010-02-15
Banner Student - Admissions | System Integration Development and Testing | Integration/Interfaces Deployed in Production | 2009-02-23 | 2010-02-15
Banner Student - Admissions | Production Simulation Testing | Production Simulation Testing Signed Off; Module Readied for Production | 2009-07-13 | 2010-01-22 | bar: Apr to Dec
Banner Student - Admissions | End User Training & Rollout | Necessary End Users Certified; Procedure Manuals Signed Off and Ready for Production Use | 2009-04-21 | 2010-01-22 | bar: Jul to Dec
Banner Student - Admissions | System Deployment and Maintenance | FHDA Organization, Maintenance Approach Readied and in Place; Plans in Place for Resolving Post-Go Live Issues | 2009-07-13 | 2010-02-15
Banner Student - Registration |  | Banner Student Module (Registration) Deployed in Production | 2008-10-16 | 2010-04-05
Banner Student - Registration | System Education | System Education completed; staff readied for subsequent implementation activities | 2009-01-19 | 2009-11-13
Banner Student - Registration | Prototype Configuration and Testing | Prototype Configured and Readied for subsequent testing and deployment activities | 2009-01-19 | 2009-11-20
Banner Student - Registration | Data Migration | All required data converted into Production | 2009-01-19 | 2010-04-05
Banner Student - Registration | Information Access | All queries and reports required for Production tested and deployed | 2009-01-19 | 2010-04-05
Banner Student - Registration | System Integration Development and Testing | Integration/Interfaces Deployed in Production | 2009-02-23 | 2010-04-05
Banner Student - Registration | End User Training & Rollout | Necessary End Users Certified; Procedure Manuals Signed Off and Ready for Production Use | 2009-04-21 | 2010-03-19 | bar: Apr to Dec
Banner Student - Registration | Production Simulation Testing | Production Simulation Testing Signed Off; Module Readied for Production | 2009-09-07 | 2010-03-19 | bar: Sep to Dec
Banner Student - Registration | System Deployment and Maintenance | FHDA Organization, Maintenance Approach Readied and in Place; Plans in Place for Resolving Post-Go Live Issues | 2009-11-02 | 2010-04-05 | bar: Nov to Dec
Banner Financial Aid |  | Banner Financial Aid Module Deployed in Production | 2008-10-06 | 2010-02-15
Banner Financial Aid | System Education | System Education completed; staff readied for subsequent implementation activities | 2009-01-26 | 2009-09-11 | bar: Feb to Sep
Banner Financial Aid | Prototype Configuration and Testing | Prototype Configured and Readied for subsequent testing and deployment activities | 2009-01-26 | 2009-10-23 | bar: Feb to Oct
Banner Financial Aid | Data Migration | All required data converted into Production | 2009-01-26 | 2010-02-15
Banner Financial Aid | Information Access | All queries and reports required for Production tested and deployed | 2009-01-26 | 2010-02-15
Banner Financial Aid | System Integration Development and Testing | Integration/Interfaces Deployed in Production | 2009-03-23 | 2010-02-15
Banner Financial Aid | End User Training & Rollout | Necessary End Users Certified; Procedure Manuals Signed Off and Ready for Production Use | 2009-04-21 | 2010-01-22 | bar: Apr to Dec
Banner Financial Aid | Production Simulation Testing | Production Simulation Testing Signed Off; Module Readied for Production | 2009-07-13 | 2010-01-22 | bar: Jul to Dec
Banner Financial Aid | System Deployment and Maintenance | FHDA Organization, Maintenance Approach Readied and in Place; Plans in Place for Resolving Post-Go Live Issues | 2009-07-13 | 2010-02-15 | bar: Jul to Dec
Banner Advancement |  | Banner Advancement Module Deployed in Production | 2010-01-18 | 2011-01-24
Banner Advancement | System Education | System Education completed; staff readied for subsequent implementation activities | 2010-02-10 | 2010-09-24
Banner Advancement | Prototype Configuration and Testing | Prototype Configured and Readied for subsequent testing and deployment activities | 2010-02-10 | 2010-09-24
Banner Advancement | Information Access | All queries and reports required for Production tested and deployed | 2010-02-10 | 2011-01-24
Banner Advancement | Data Migration | All required data converted into Production | 2011-03-29 | 2011-01-24
Banner Advancement | System Integration Development and Testing | Integration/Interfaces Deployed in Production | 2010-05-31 | 2011-01-24
Banner Advancement | Production Simulation Testing | Production Simulation Testing Signed Off; Module Readied for Production | 2010-08-16 | 2011-01-10
Banner Advancement | End User Training & Rollout | Necessary End Users Certified; Procedure Manuals Signed Off and Ready for Production Use | 2010-08-16 | 2011-01-10
Banner Advancement | System Deployment and Maintenance | FHDA Organization, Maintenance Approach Readied and in Place; Plans in Place for Resolving Post-Go Live Issues | 2010-08-16 | 2011-01-24
BDMS (Xtender) |  | BDMS Deployed in Production | 2009-08-10 | 2010-04-05 | bar: Aug to Dec
BDMS (Xtender) | Imaging Needs Analysis | Imaging Needs Analysis Delivered and Reviewed | 2009-08-10 | 2009-09-04 | bar: Aug to Sep
BDMS (Xtender) | BDMS Installation | BDMS Installed in Test Environment | 2009-08-24 | 2009-09-04 | bar: Aug to Sep
BDMS (Xtender) | BDMS Training | BDMS Administrators and Users Readied | 2009-12-10 | 2010-03-19 | bar: Dec
BDMS (Xtender) | BDMS Deployment | BDMS Deployed in Production | 2009-12-10 | 2010-04-05 | bar: Dec
ODS |  | ODS Deployed in Production | 2008-11-17 | 2010-04-05
ODS | Information Access Strategy and Assessment | Information Access Strategy and Assessment Delivered and Reviewed | 2008-11-17 | 2008-12-08
ODS | ODS Installation | ODS Installed in Test Environment | 2009-01-20 | 2009-02-13 | bar: Feb
ODS | ODS Training | ODS Administrators and Users Readied | 2009-02-03 | 2009-12-15
ODS | ODS Deployment | ODS Deployed in Production | 2009-02-16 | 2010-04-05
EDW |  | EDW Deployed in Production | 2008-11-17 | 2010-04-05
EDW | Information Access Strategy and Assessment | Information Access Strategy and Assessment Delivered and Reviewed | 2008-11-17 | 2008-12-08
EDW | EDW Installation | EDW Installed in Test Environment | 2009-06-22 | 2009-07-24 | bar: Jun to Jul
EDW | EDW Training | EDW Administrators and Users Readied | 2009-06-22 | 2009-11-20 | bar: Jun to Nov
EDW | EDW Deployment | EDW Deployed in Production | 2009-11-16 | 2010-03-15 | bar: Nov to Dec
DegreeWorks |  | DegreeWorks Deployed in Production | 2010-06-08 | 2011-01-17
DegreeWorks | Planning | Detailed Plans for DW Implementation Developed and Reviewed | 2010-06-08 | 2010-06-19
DegreeWorks | Software Installation | DegreeWorks Installed in Test Environment | 2010-07-20 | 2010-07-24
DegreeWorks | Catalog Authentication | Catalog Authenticated and Readied for Scribing | 2010-06-22 | 2010-07-17
DegreeWorks | Scribing and Code Validation | Catalog Scribed and Readied for DegreeWorks Use | 2010-07-20 | 2010-09-20
DegreeWorks | Data Preparation, Training and Consulting | Data Readied; FHDA Trained and Readied for DegreeWorks Usage | 2010-08-02 | 2010-10-20
DegreeWorks | Web localizations | Local Modifications to Web Screens Applied and Tested | 2010-09-20 | 2010-11-19
DegreeWorks | Cut Over to Production | DegreeWorks Deployed in Production | 2010-10-12 | 2011-01-17
Total
Advancement
|  | Marie Fox-Ellison |  | 1280 | [16 empty] | 40 | 80 | 80 | 80 | 80 | 80 | 120 | 120 | 120 | 120 | 120 | 120 | 120
|  | Extended Advancement Team |  | 2240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 160 | 160 | 160 | 160 | 160 | 200 | 200 | 200 | 200 | 200 | 200 | 200
Finance
|  | Hector Quinonez |  | 2200 | 200 | 80 | 80 | 80 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 40 | 40 | 40
|  | Extended Finance Team |  | 7760 | 0 | 520 | 520 | 520 | 520 | 520 | 840 | 840 | 840 | 520 | 520 | 160 | 160 | 160 | 320 | 320 | 160 | 160 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Financial Aid
|  | Cindy Castillo |  | 2560 | 200 | 80 | 80 | 80 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 80 | 40 | 40 | 40 | 40 | 40 | 40
|  | Extended Financial Aid Team |  | 5960 | 0 | 0 | 0 | 0 | 280 | 320 | 320 | 320 | 320 | 320 | 320 | 320 | 720 | 720 | 640 | 320 | 320 | 320 | 200 | 200 | 0 | 0 | 0 | 0 | 0 | 0
Human Resources/Payroll
|  | Kim Chief Elk |  | 2760 | 200 | 80 | 80 | 80 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 80 | 80 | 40 | 40 | 40 | 40 | 80 | 80 | 80 | 80
|  | Extended HR Team |  | 7680 | 0 | 0 | 480 | 480 | 480 | 240 | 480 | 480 | 480 | 480 | 480 | 480 | 480 | 480 | 720 | 480 | 480 | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Instructional Support
|  | Gertrude Gregorio |  | 2760 | 200 | 80 | 80 | 80 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 80 | 80 | 40 | 40 | 40 | 40 | 40 | 40
|  | Extended Instructional Support Team |  | 4040 | 0 | 0 | 0 | 0 | 280 | 280 | 400 | 400 | 280 | 440 | 320 | 280 | 280 | 280 | 280 | 280 | 80 | 80 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Luminis
|  | Kurt Hueg |  | 1760 |  |  | 40 | 40 | 80 | 80 | 80 | 80 | 80 | 80 | 40 | 40 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 40 | 40 | 80 | 80 | 80 | 80 | 40 | 40 | 80
|  | Drake Lewis |  | 2120 | 200 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 40 | 40 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 40 | 40 | 80 | 80 | 80 | 80 | 40 | 40 | 80
|  | Extended LuminisTeam |  | 6712 | 80 | 0 | 80 | 192 | 320 | 680 | 260 | 320 | 320 | 220 | 260 | 300 | 380 | 300 | 340 | 340 | 340 | 300 | 300 | 180 | 180 | 180 | 180 | 220 | 220 | 220 | 0 | 0 | 0
Student - Admissions and Records
|  | Kathleen Moberg |  | 2920 | 200 | 80 | 80 | 80 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 40 | 40 | 40 | 80 | 80 | 80 | 80
|  | Extended Student Administration Team |  | 8760 | 0 | 0 | 0 | 360 | 480 | 480 | 480 | 280 | 280 | 320 | 600 | 360 | 80 | 120 | 720 | 720 | 640 | 640 | 600 | 600 | 160 | 160 | 160 | 120 | 120 | 120 | 80 | 80 | 0
Reporting and Data Warehouse
|  | Bob Barr |  | 1880 | 200 | 40 | 40 | 40 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
|  | Extended Reporting Team |  | 1920 | 0 | 0 | 0 | 0 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 0
Technical
|  | Joe Lampo |  | 3320 | 200 | 80 | 80 | 80 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120
|  | Tom Roza |  | 3320 | 200 | 80 | 80 | 80 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120
|  | Extended Techncial Team |  | 6700 | 0 | 40 | 80 | 40 | 100 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 0
Network
|  | Sharon Luciw |  | 960 |  |  |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
|  | Extended Network Team |  | 2400 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0
Project Management
|  | Kathy Kyne |  | 2640 | 240 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
| Total Months | Total Hours |  | 84652 | 2120 | 1320 | 1960 | 2392 | 3840 | 4180 | 4440 | 4300 | 4180 | 3960 | 4080 | 3440 | 3720 | 3680 | 4640 | 4080 | 3720 | 3840 | 3120 | 2680 | 1880 | 1840 | 1880 | 1880 | 1920 | 1840 | 1540 | 1620 | 400 | 80 | 80
NOTE: These estimates are a first draft, and are intended to faciliate discussion on FHDA staffing levels. They have not yet been reviewed and vetted with the various teams. As such, they will need further discussion and refinement.

## Waterfall - Detailed Team
Major Activity | Major Phase | Major Milestone | Start Date | Finish Date | 2008 PTD | Oct | Nov | Dec | 2009 Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | 2010 Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | 2011 Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Software Installation |  | Oracle, Banner and Luminis Installed on FHDA hardware; Knowledge Transferred to FHDA IT Organization on Configuration and Operations | 2008-07-21 | 2008-12-05
Software Installation | Installation Preparation | Pre-Install Checklist Verified | 2008-09-22 | 2008-09-26
Software Installation | Conduct Installation | Oracle, Banner and Luminis Installed on FHDA hardware | 2008-10-01 | 2008-11-25
Software Installation | Oracle/Banner Installation Review | Knowledge Transferred to FHDA IT Organization on Configuration and Operations | 2008-10-22 | 2008-12-05
Software Installation | Luminis Platform Installation Review | Knowledge Transferred to FHDA IT Organization on Configuration and Operations | 2008-07-21 | 2008-12-05
Business Process Analysis |  | Selected Business Processes Analyzed and Documented | 2008-09-15 | 2008-12-29
Business Process Analysis | BPA Planning | Agendas for BPA On-site Reviewed | 2008-09-15 | 2008-10-06
Business Process Analysis | BPA On-site Analysis | On-site BPA Analysis Conducted | 2008-10-20 | 2008-12-12
Business Process Analysis | BPA Write-up, Follow-up, and Document Preparation | Future State Process Models and Recommendations Document Delivered and Reviewed | 2008-10-27 | 2008-12-29
Identity and Access Management |  | Identity Management Solution Deployed in Production | 2008-10-13 | 2009-06-17 | bar: Feb to Jun
Identity and Access Management | Assessment | Identity Management Strategy in Place | 2008-10-13 | 2008-11-21
Identity and Access Management | Planning | Detailed Plans, Specifications for IAM Implementation Developed and Reviewed | 2009-01-16 | 2009-02-27
Identity and Access Management | Baseline Solution Implementation | Baseline Identity Management Code Developed and Tested | 2008-12-15 | 2009-02-27 | bar: Feb
Identity and Access Management | Baseline Solution Deployment | Baseline Identity Management Solution Deployed in Production | 2009-03-09 | 2009-06-17 | bar: Mar to Jun
Identity and Access Management | Enhanced Solution Implementation | Enhanced Identity Management Code Developed and Tested | 2009-08-03 | 2009-09-04 | bar: Aug to Sep
Identity and Access Management | Enhanced Solution Deployment | Enhanced Identity Management Solution Deployed in Production | 2009-09-07 | 2009-11-06 | bar: Sep to Nov
Integration/Interfaces |  | Integration and Interfaces Deployed in Production | 2008-10-06 | 2011-01-31
Integration/Interfaces | Integration Assessment | Integration Assessment Document Delivered | 2008-10-06 | 2008-12-05
Luminis IV Platform Phase 1 - Finance Users |  | Luminis Platform Deployed in Production | 2008-09-03 | 2009-07-02 | bar: Feb to Jul
Luminis IV Platform Phase 1 - Finance Users | Assessment | TPW Delivered, Project Definition Document Delivered | 2008-09-22 | 2008-10-15
Luminis IV Platform Phase 1 - Finance Users | Planning | Organizational and Content Planning Completed | 2008-11-17 | 2008-12-15
Luminis IV Platform Phase 1 - Finance Users | Implementation | Test Environment Installed | 2008-10-15 | 2008-12-05
Luminis IV Platform Phase 1 - Finance Users | Implementation | System Education, CAT Training Completed | 2008-11-03 | 2009-02-19 | bar: Feb
Luminis IV Platform Phase 1 - Finance Users | Implementation | Production Environment Installed | 2009-02-23 | 2009-04-08 | bar: Feb to Apr
Luminis IV Platform Phase 1 - Finance Users | Implementation | Luminis Platform Certified | 2009-05-25 | 2009-06-26 | bar: May to Jun
Luminis IV Platform Phase 1 - Finance Users | Implementation | Technical and Operational Readiness Validated | 2009-06-29 | 2009-07-02 | bar: Jun to Jul
Luminis IV Platform Phase 2 - HR Users | Implementation | Organization Readied and Content to be Provided to HR Users Completed | 2009-08-03 | 2010-01-01 | bar: Sep to Dec
Luminis IV Platform Phase 3 - Student Users | Implementation | Organization Readied and Content to be Provided to Student Users Completed | 2009-09-01 | 2010-02-15 | bar: Oct to Dec
Luminis IV Platform Phase 1 - Finance Users | Close-out | Lessons Learned and Transition to Maintenance Strategy | 2009-07-05 | 2009-07-09 | bar: Aug
Banner Finance Phase 1 - General Accounting |  | Banner Finance Module (General Accounting) Deployed in Production | 2008-10-10 | 2009-07-01 | bar: Feb to Jul
Banner Finance Phase 1 - General Accounting | System Education | System Education completed; staff readied for subsequent implementation activities | 2008-10-27 | 2008-05-15 | bar: Feb to May
Banner Finance Phase 1 - General Accounting | Prototype Configuration and Testing | Completed Chart of Accounts, Validated Accounting Process | 2008-10-27 | 2009-02-20 | bar: Feb
Banner Finance Phase 1 - General Accounting | Prototype Configuration and Testing | Banner Finance data base populated sufficiently to support ODS report development | 2009-02-20 | 2009-03-15 | bar: Feb to Mar
Banner Finance Phase 1 - General Accounting | Prototype Configuration and Testing | Banner 8 Migration Plan Completed | 2009-03-01 | 2009-03-15 | bar: Mar
Banner Finance Phase 1 - General Accounting | Prototype Configuration and Testing | Banner 8 Issues Resolves | 2009-03-18 | 2009-04-15 | bar: Mar to Apr
Banner Finance Phase 1 - General Accounting | Data Migration | Balance, Budget Loaded; Vendors Entered | 2009-04-18 | 2009-04-27 | bar: Apr
Banner Finance Phase 1 - General Accounting | Production Simulation Testing | Parralel 1 Day Validated Month End Run Validated | 2009-05-01 | 2009-05-14 | bar: May
Banner Finance Phase 1 - General Accounting | Information Access | All queries and reports required for Production tested and deployed | 2009-03-01 | 2009-06-12 | bar: Mar to Jun
Banner Finance Phase 1 - General Accounting | System Integration Development and Testing | Integration/Interfaces Deployed in Production | 2009-02-16 | 2009-06-12 | bar: Feb to Jun
Banner Finance Phase 1 - General Accounting | End User Training & Rollout | Necessary End Users Certified; Procedure Manuals Signed Off and Ready for Production Use | 2009-02-16 | 2009-06-12 | bar: May to Jun
Banner Finance Phase 1 - General Accounting | System Deployment and Maintenance | FHDA Organization, Maintenance Approach Readied and in Place; Plans in Place for Resolving Post-Go Live Issues | 2009-05-25 | 2009-07-10 | bar: May to Jul
Banner Finance Phase 2 - Budget |  | Banner Finance Module (Budget) Deployed in Production | 2009-08-17 | 2010-02-01 | bar: Aug to Dec
Banner Finance Phase 2 - Budget | System Education | System Education completed; staff readied for subsequent implementation activities | 2009-08-17 | 2009-08-21 | bar: Aug
Banner Finance Phase 2 - Budget | Prototype Configuration and Testing | Prototype Configured and Readied for subsequent testing and deployment activities | 2009-08-17 | 2009-10-30 | bar: Aug to Oct
Banner Finance Phase 2 - Budget | Data Migration | All required data converted into Production | 2009-08-17 | 2009-10-30 | bar: Aug to Oct
Banner Finance Phase 2 - Budget | Information Access | All queries and reports required for Production tested and deployed | 2009-08-17 | 2009-12-04 | bar: Aug to Dec
Banner Finance Phase 2 - Budget | System Integration Development and Testing | Integration/Interfaces Deployed in Production | 2009-08-17 | 2009-12-04 | bar: Aug to Dec
Banner Finance Phase 2 - Budget | Production Simulation Testing | Production Simulation Testing Signed Off; Module Readied for Production | 2009-10-05 | 2009-12-18 | bar: Oct to Dec
Banner Finance Phase 2 - Budget | End User Training & Rollout | Necessary End Users Certified; Procedure Manuals Signed Off and Ready for Production Use | 2009-10-05 | 2009-12-18
Banner Finance Phase 2 - Budget | System Deployment and Maintenance | FHDA Organization, Maintenance Approach Readied and in Place; Plans in Place for Resolving Post-Go Live Issues | 2010-01-04 | 2010-02-12
Banner Human Resources |  | Banner Human Resources Module Deployed in Production | 2008-10-21 | 2010-01-04
Banner Human Resources | System Education | System Education completed; staff readied for subsequent implementation activities | 2008-11-10 | 2009-08-14 | bar: Feb to Aug
Banner Human Resources | Prototype Configuration and Testing | Prototype Configured and Readied for subsequent testing and deployment activities | 2008-11-10 | 2009-10-02 | bar: Feb to Oct
Banner Human Resources | Information Access | All queries and reports required for Production tested and deployed | 2008-11-10 | 2009-11-27
Banner Human Resources | Data Migration | All required data converted into Production | 2009-03-23 | 2009-11-27 | bar: Mar to Nov
Banner Human Resources | System Integration Development and Testing | Integration/Interfaces Deployed in Production | 2009-03-23 | 2010-01-04
Banner Human Resources | Production Simulation Testing | Production Simulation Testing Signed Off; Module Readied for Production | 2009-08-10 | 2009-11-17 | bar: Aug to Nov
Banner Human Resources | End User Training & Rollout | Necessary End Users Certified; Procedure Manuals Signed Off and Ready for Production Use | 2009-08-10 | 2009-12-18 | bar: Aug to Dec
Banner Human Resources | System Deployment and Maintenance | FHDA Organization, Maintenance Approach Readied and in Place; Plans in Place for Resolving Post-Go Live Issues | 2009-11-16 | 2010-01-15 | bar: Nov to Dec
Banner Student - Admissions |  | Banner Student Module (Admissions) Deployed in Production | 2008-10-06 | 2010-02-15
Banner Student - Admissions | System Education | System Education completed; staff readied for subsequent implementation activities | 2009-01-19 | 2009-09-04 | bar: Feb to Sep
Banner Student - Admissions | Prototype Configuration and Testing | Prototype Configured and Readied for subsequent testing and deployment activities | 2009-01-19 | 2009-10-16 | bar: Feb to Oct
Banner Student - Admissions | Data Migration | All required data converted into Production | 2009-01-19 | 2009-02-15
Banner Student - Admissions | Information Access | All queries and reports required for Production tested and deployed | 2009-01-19 | 2010-02-15
Banner Student - Admissions | System Integration Development and Testing | Integration/Interfaces Deployed in Production | 2009-02-23 | 2010-02-15
Banner Student - Admissions | Production Simulation Testing | Production Simulation Testing Signed Off; Module Readied for Production | 2009-07-13 | 2010-01-22 | bar: Apr to Dec
Banner Student - Admissions | End User Training & Rollout | Necessary End Users Certified; Procedure Manuals Signed Off and Ready for Production Use | 2009-04-21 | 2010-01-22 | bar: Jul to Dec
Banner Student - Admissions | System Deployment and Maintenance | FHDA Organization, Maintenance Approach Readied and in Place; Plans in Place for Resolving Post-Go Live Issues | 2009-07-13 | 2010-02-15
Banner Student - Registration |  | Banner Student Module (Registration) Deployed in Production | 2008-10-16 | 2010-04-05
Banner Student - Registration | System Education | System Education completed; staff readied for subsequent implementation activities | 2009-01-19 | 2009-11-13
Banner Student - Registration | Prototype Configuration and Testing | Prototype Configured and Readied for subsequent testing and deployment activities | 2009-01-19 | 2009-11-20
Banner Student - Registration | Data Migration | All required data converted into Production | 2009-01-19 | 2010-04-05
Banner Student - Registration | Information Access | All queries and reports required for Production tested and deployed | 2009-01-19 | 2010-04-05
Banner Student - Registration | System Integration Development and Testing | Integration/Interfaces Deployed in Production | 2009-02-23 | 2010-04-05
Banner Student - Registration | End User Training & Rollout | Necessary End Users Certified; Procedure Manuals Signed Off and Ready for Production Use | 2009-04-21 | 2010-03-19 | bar: Apr to Dec
Banner Student - Registration | Production Simulation Testing | Production Simulation Testing Signed Off; Module Readied for Production | 2009-09-07 | 2010-03-19 | bar: Sep to Dec
Banner Student - Registration | System Deployment and Maintenance | FHDA Organization, Maintenance Approach Readied and in Place; Plans in Place for Resolving Post-Go Live Issues | 2009-11-02 | 2010-04-05 | bar: Nov to Dec
Banner Financial Aid |  | Banner Financial Aid Module Deployed in Production | 2008-10-06 | 2010-02-15
Banner Financial Aid | System Education | System Education completed; staff readied for subsequent implementation activities | 2009-01-26 | 2009-09-11 | bar: Feb to Sep
Banner Financial Aid | Prototype Configuration and Testing | Prototype Configured and Readied for subsequent testing and deployment activities | 2009-01-26 | 2009-10-23 | bar: Feb to Oct
Banner Financial Aid | Data Migration | All required data converted into Production | 2009-01-26 | 2010-02-15
Banner Financial Aid | Information Access | All queries and reports required for Production tested and deployed | 2009-01-26 | 2010-02-15
Banner Financial Aid | System Integration Development and Testing | Integration/Interfaces Deployed in Production | 2009-03-23 | 2010-02-15
Banner Financial Aid | End User Training & Rollout | Necessary End Users Certified; Procedure Manuals Signed Off and Ready for Production Use | 2009-04-21 | 2010-01-22 | bar: Apr to Dec
Banner Financial Aid | Production Simulation Testing | Production Simulation Testing Signed Off; Module Readied for Production | 2009-07-13 | 2010-01-22 | bar: Jul to Dec
Banner Financial Aid | System Deployment and Maintenance | FHDA Organization, Maintenance Approach Readied and in Place; Plans in Place for Resolving Post-Go Live Issues | 2009-07-13 | 2010-02-15 | bar: Jul to Dec
Banner Advancement |  | Banner Advancement Module Deployed in Production | 2010-01-18 | 2011-01-24
Banner Advancement | System Education | System Education completed; staff readied for subsequent implementation activities | 2010-02-10 | 2010-09-24
Banner Advancement | Prototype Configuration and Testing | Prototype Configured and Readied for subsequent testing and deployment activities | 2010-02-10 | 2010-09-24
Banner Advancement | Information Access | All queries and reports required for Production tested and deployed | 2010-02-10 | 2011-01-24
Banner Advancement | Data Migration | All required data converted into Production | 2011-03-29 | 2011-01-24
Banner Advancement | System Integration Development and Testing | Integration/Interfaces Deployed in Production | 2010-05-31 | 2011-01-24
Banner Advancement | Production Simulation Testing | Production Simulation Testing Signed Off; Module Readied for Production | 2010-08-16 | 2011-01-10
Banner Advancement | End User Training & Rollout | Necessary End Users Certified; Procedure Manuals Signed Off and Ready for Production Use | 2010-08-16 | 2011-01-10
Banner Advancement | System Deployment and Maintenance | FHDA Organization, Maintenance Approach Readied and in Place; Plans in Place for Resolving Post-Go Live Issues | 2010-08-16 | 2011-01-24
BDMS (Xtender) |  | BDMS Deployed in Production | 2009-08-10 | 2010-04-05 | bar: Aug to Dec
BDMS (Xtender) | Imaging Needs Analysis | Imaging Needs Analysis Delivered and Reviewed | 2009-08-10 | 2009-09-04 | bar: Aug to Sep
BDMS (Xtender) | BDMS Installation | BDMS Installed in Test Environment | 2009-08-24 | 2009-09-04 | bar: Aug to Sep
BDMS (Xtender) | BDMS Training | BDMS Administrators and Users Readied | 2009-12-10 | 2010-03-19 | bar: Dec
BDMS (Xtender) | BDMS Deployment | BDMS Deployed in Production | 2009-12-10 | 2010-04-05 | bar: Dec
ODS |  | ODS Deployed in Production | 2008-11-17 | 2010-04-05
ODS | Information Access Strategy and Assessment | Information Access Strategy and Assessment Delivered and Reviewed | 2008-11-17 | 2008-12-08
ODS | ODS Installation | ODS Installed in Test Environment | 2009-01-20 | 2009-02-13 | bar: Feb
ODS | ODS Training | ODS Administrators and Users Readied | 2009-02-03 | 2009-12-15
ODS | ODS Deployment | ODS Deployed in Production | 2009-02-16 | 2010-04-05
EDW |  | EDW Deployed in Production | 2008-11-17 | 2010-04-05
EDW | Information Access Strategy and Assessment | Information Access Strategy and Assessment Delivered and Reviewed | 2008-11-17 | 2008-12-08
EDW | EDW Installation | EDW Installed in Test Environment | 2009-06-22 | 2009-07-24 | bar: Jun to Jul
EDW | EDW Training | EDW Administrators and Users Readied | 2009-06-22 | 2009-11-20 | bar: Jun to Nov
EDW | EDW Deployment | EDW Deployed in Production | 2009-11-16 | 2010-03-15 | bar: Nov to Dec
DegreeWorks |  | DegreeWorks Deployed in Production | 2010-06-08 | 2011-01-17
DegreeWorks | Planning | Detailed Plans for DW Implementation Developed and Reviewed | 2010-06-08 | 2010-06-19
DegreeWorks | Software Installation | DegreeWorks Installed in Test Environment | 2010-07-20 | 2010-07-24
DegreeWorks | Catalog Authentication | Catalog Authenticated and Readied for Scribing | 2010-06-22 | 2010-07-17
DegreeWorks | Scribing and Code Validation | Catalog Scribed and Readied for DegreeWorks Use | 2010-07-20 | 2010-09-20
DegreeWorks | Data Preparation, Training and Consulting | Data Readied; FHDA Trained and Readied for DegreeWorks Usage | 2010-08-02 | 2010-10-20
DegreeWorks | Web localizations | Local Modifications to Web Screens Applied and Tested | 2010-09-20 | 2010-11-19
DegreeWorks | Cut Over to Production | DegreeWorks Deployed in Production | 2010-10-12 | 2011-01-17
Total
Advancement
|  | Marie Fox-Ellison |  | 1280 | [16 empty] | 40 | 80 | 80 | 80 | 80 | 80 | 120 | 120 | 120 | 120 | 120 | 120 | 120
|  | Extended Advancement Team |  | 2240 | [16 empty] | 40 | 160 | 160 | 160 | 160 | 160 | 200 | 200 | 200 | 200 | 200 | 200 | 200
Finance
|  | Hector Quinonez |  | 2200 | 200 | 80 | 80 | 80 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 40 | 40 | 40
|  | Budget |  |  |  | 40 | 40 | 40 | 40 | 40 | 80 | 80 | 80 | 40 | 40 | 40 | 40 | 40 | 80 | 80 | 40 | 40 | 40
|  | Accounts Payable |  |  |  | 40 | 40 | 40 | 40 | Feb: 40; Mar: 80; Apr: 80; May: 80; Jun: 40; Jul: 40
|  | General Ledger |  |  |  | 40 | 40 | 40 | 40 | Feb: 40; Mar: 80; Apr: 80; May: 80; Jun: 40; Jul: 40
|  | Purchasing |  |  |  | 40 | 40 | 40 | 40 | 40 | 80 | 80 | 80 | 40 | 40 | 40 | 40 | 40 | 80 | 80 | 40 | 40 | 40
|  | Facilities |  |  |  | 40 | 40 | 40 | 40 | 40 | 80 | 80 | 80 | 40 | 40 | 40 | 40 | 40 | 80 | 80 | 40 | 40 | 40
|  | Foundation |  |  |  | 40 | 40 | 40 | 40 | Feb: 40; Mar: 80; Apr: 80; May: 80; Jun: 40; Jul: 40
|  | HR |  |  |  | 40 | 40 | 40 | 40 | 40 | 80 | 80 | 80 | 40 | 40 | 40 | 40 | 40 | 80 | 80 | 40 | 40 | 40
|  | Web Services |  |  |  | 40 | 40 | 40 | 40 | Feb: 40; Mar: 40; Apr: 40; May: 40; Jun: 40; Jul: 40
|  | Facility |  |  |  | 40 | 40 | 40 | 40 | Feb: 40; Mar: 40; Apr: 40; May: 40; Jun: 40; Jul: 40
|  | Payroll |  |  |  | 40 | 40 | 40 | 40 | Feb: 40; Mar: 80; Apr: 80; May: 80; Jun: 40; Jul: 40
|  | Financial Aid |  |  |  | 40 | 40 | 40 | 40 | Feb: 40; Mar: 40; Apr: 40; May: 40; Jun: 40; Jul: 40
|  | Student Accounting |  |  |  | 40 | 40 | 40 | 40 | Feb: 40; Mar: 40; Apr: 40; May: 40; Jun: 40; Jul: 40
|  | Admissions and Records |  |  |  | 40 | 40 | 40 | 40 | Feb: 40; Mar: 40; Apr: 40; May: 40; Jun: 40; Jul: 40
|  | Extended Finance Team |  | 7760 | 0 | 520 | 520 | 520 | 520 | 520 | 840 | 840 | 840 | 520 | 520 | 160 | 160 | 160 | 320 | 320 | 160 | 160 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Financial Aid
|  | Cindy Castillo |  | 2560 | 200 | 80 | 80 | 80 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 80 | 40 | 40 | 40 | 40 | 40 | 40
|  | Financial aid | [6 empty] | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 320 | 320 | 320 | 160 | 160 | 160 | 80 | 80
|  | HR/Payroll | [6 empty] | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 160 | 160 | 80 | 80 | 80 | 80 | 40 | 40
|  | Student accounts/finance/cashiering | [6 empty] | 40 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 240 | 240 | 240 | 80 | 80 | 80 | 80 | 80
|  | Extended Financial Aid Team |  | 5960 | 0 | 0 | 0 | 0 | 280 | 320 | 320 | 320 | 320 | 320 | 320 | 320 | 720 | 720 | 640 | 320 | 320 | 320 | 200 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Human Resources/Payroll
|  | Kim Chief Elk |  | 2760 | 200 | 80 | 80 | 80 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 80 | 80 | 40 | 40 | 40 | 40 | 80 | 80 | 80 | 80
|  | Payroll |  |  |  |  | 80 | 80 | 80 | 40 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 120 | 80 | 80 | 80
|  | Benefits |  |  |  |  | 80 | 80 | 80 | 40 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 120 | 80 | 80 | 80
|  | Budget |  |  |  |  | 80 | 80 | 80 | 40 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 120 | 80 | 80 | 80
|  | Financial Aid |  |  |  |  | 80 | 80 | 80 | 40 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 120 | 80 | 80 | 80
|  | HR: hiring, personnel records, employment tracking |  |  |  |  | 80 | 80 | 80 | 40 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 120 | 80 | 80 | 80
|  | Diversity and Equity |  |  |  |  | 80 | 80 | 80 | 40 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 120 | 80 | 80 | 80
|  | Extended HR Team |  | 7680 | 0 | 0 | 480 | 480 | 480 | 240 | 480 | 480 | 480 | 480 | 480 | 480 | 480 | 480 | 720 | 480 | 480 | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Instructional Support
|  | Gertrude Gregorio |  | 2760 | 200 | 80 | 80 | 80 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 80 | 80 | 40 | 40 | 40 | 40 | 40 | 40
|  | Curriculum/catalog/schedule of classes | [6 empty] | 40 | 40 | 120 | 120 | 40 | 80 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
|  | Scheduling/staff assignment | [6 empty] | 40 | 40 | 80 | 80 | 40 | 80 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
|  | Marketing | [6 empty] | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
|  | Facilities/Room Scheduling | [6 empty] | 40 | 40 | 40 | 40 | 40 | 80 | 40 | 40 | 40 | 40 | 40 | 40
|  | HR | [6 empty] | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
|  | Faculty Load | [6 empty] | 40 | 40 | 40 | 40 | 40 | 80 | 80 | 40 | 40 | 40 | 40 | 40
|  | Bookstore | [6 empty] | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
|  | Extended Instructional Support Team |  | 4040 | 0 | 0 | 0 | 0 | 280 | 280 | 400 | 400 | 280 | 440 | 320 | 280 | 280 | 280 | 280 | 280 | 80 | 80 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Luminis
|  | Kurt Hueg |  | 1760 |  |  | 40 | 40 | 80 | 80 | 80 | 80 | 80 | 80 | 40 | 40 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 40 | 40 | 80 | 80 | 80 | 80 | 40 | 40 | 80
|  | Drake Lewis |  | 2120 | 200 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 40 | 40 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 40 | 40 | 80 | 80 | 80 | 80 | 40 | 40 | 80
|  | Campus/district webmasters/designers |  |  | 10 |  | 10 | 24 | 40 | 120 | 120 | 40 | 40 | 80 | 40 | 40 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 40 | 40 | 40 | 40 | 80 | 80 | 80
|  | Marketing |  |  | 10 |  | 10 | 24 | 40 | 80 | 20 | 40 | 40 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
|  | District Public Relations |  |  | 10 |  | 10 | 24 | 40 | 80 | 20 | 40 | 40 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
|  | Student Services and Financial Aid |  |  | 10 |  | 10 | 24 | 40 | 80 |  | 40 | 40 |  | 40 | 80 | 80 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
|  | Finance |  |  | 10 |  | 10 | 24 | 40 | 80 | 80 | 40 | 40 | 40 | 40 |  |  |  | 40 | 40 | 40 | 40 | 40
|  | Training/Video |  |  | 10 |  | 10 | 24 | 40 | 80 | 20 | 40 | 40 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
|  | Faculty |  |  | 10 |  | 10 | 24 | 40 | 80 |  | 40 | 40 |  | 40 | 80 | 80 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
|  | HR |  |  | 10 |  | 10 | 24 | 40 | 80 |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
|  | Extended Luminis Team |  | 6712 | 80 | 0 | 80 | 192 | 320 | 680 | 260 | 320 | 320 | 220 | 260 | 300 | 380 | 300 | 340 | 340 | 340 | 300 | 300 | 180 | 180 | 180 | 180 | 220 | 220 | 220 | 0 | 0
Student - Admissions and Records
|  | Kathleen Moberg |  | 2920 | 200 | 80 | 80 | 80 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 40 | 40 | 40 | 80 | 80 | 80 | 80
|  | Student accounts | [5 empty] | 24 | 32 | 40 | 32 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 80 | 80 | 40 | 40 | 40 | 40
|  | Admissions and Records | [5 empty] | 24 | 32 | 40 | 32 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 80 | 80 | 40 | 40 | 40 | 40
|  | Degree Audit | [5 empty] | 24 | 32 | 40 | 32 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40
|  | Instruction | [5 empty] | 24 | 32 | 40 | 32 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40
|  | Counseling/Articulation/Matriculation | [5 empty] | 24 | 32 | 40 | 32 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 160 | 160 | 160 | 120 | 120 | 120 | 80 | 80 | 80
|  | Assessment | [5 empty] | 24 | 32 | 40 | 32 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40
|  | Curriculum/Distance Learning | [5 empty] | 24 | 32 | 40 | 32 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40
|  | Continuing Education | [5 empty] | 24 | 32 | 40 | 32 | 40 | 40 | 0 | 40 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40
|  | Scheduling | [5 empty] | 24 | 32 | 40 | 32 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40
|  | Faculty | [5 empty] | 24 | 32 | 40 | 32 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40
|  | Students | [5 empty] | 24 | 32 | 40 | 32 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40
|  | Special programs: DSS, EOPS, Athletes | [5 empty] | 24 | 32 | 40 | 32 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40
|  | International students | [5 empty] | 24 | 32 | 0 | 32 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40
|  | Bookstore | [5 empty] | 24 | 32 | 0 | 32 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40
|  | Institutional Research (hours on Reporting) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 0 | 0
|  | Finance | [5 empty] | 24 | 32 | 0 | 32 | 0 | 0 | 40 | 40 | 40 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40
|  | Extended Student Administration Team |  | 8760 | 0 | 0 | 0 | 360 | 480 | 480 | 480 | 280 | 280 | 320 | 600 | 360 | 80 | 120 | 720 | 720 | 640 | 640 | 600 | 600 | 160 | 160 | 160 | 120 | 120 | 120 | 80 | 80
Reporting and Data Warehouse
|  | Bob Barr |  | 1880 | 200 | 40 | 40 | 40 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
|  | Institutional Research | [6 empty] | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
|  | Representatives from the core teams | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Mandated reporting | [6 empty] | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
Data standards/policies
Marketing/Public Information
|  | Extended Reporting Team |  | 1920 | 0 | 0 | 0 | 0 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
Technical
|  | Joe Lampo |  | 3320 | 200 | 80 | 80 | 80 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120
|  | Tom Roza |  | 3320 | 200 | 80 | 80 | 80 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120
|  | Access |  |  |  | 40 | 40 | 40 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
|  | Interconnection | [6 empty] | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
|  | Data Migration | [6 empty] | 20 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
|  | Reporting (ODS) | [6 empty] | 20 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
Training
|  | Third party integration |  |  |  |  | 40 |  | 20 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
|  | Extended Techncial Team |  | 6700 | 0 | 40 | 80 | 40 | 100 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280 | 280
Network
|  | Sharon Luciw |  | 960 |  |  |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
|  | Connectivity | [6 empty] | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
|  | Security | [6 empty] | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
|  | Desk top Support | [6 empty] | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
|  | Performance | [6 empty] | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
|  | Help Desk | [6 empty] | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
|  | Extended Network Team |  | 2400 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Project Management
|  | Kathy Kyne |  | 2640 | 240 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
|  | Total Hours |  | 84652 | 2120 | 1320 | 1960 | 2392 | 3840 | 4180 | 4440 | 4300 | 4180 | 3960 | 4080 | 3440 | 3720 | 3680 | 4640 | 4080 | 3720 | 3840 | 3120 | 2680 | 1880 | 1840 | 1880 | 1880 | 1920 | 1840 | 1540 | 1620 | 400 | 80 | 80
NOTE: These estimates are a first draft, and are intended to faciliate discussion on FHDA staffing levels. They have not yet been reviewed and vetted with the various teams. As such, they will need further discussion and refinement.