## IDM, GP, Entity Migration Tasks
Area | Task / Milestone Name | Target Date | Resource Assigned | Status
IDM | Install UDC Provisioning Software | TBD | SGHE | To be done
IDM | Test install Banner Enterprise Identity Services | TBD | SGHE | To be done
IDM | Provide Identity Profile for Student (PLUS) | 2009-02-09 | FHDA | To be done
IDM | Provide Identity Profile for Employee (PLUS) | 2009-02-09 | FHDA | To be done
IDM | Provide Identity Profile for Alumni (PLUS - if applicable) | 2009-02-09 | FHDA | To be done
IDM | Determine Percentage of duplicate identities in Student file | 2009-02-13 | FHDA | To be done
IDM | Determine Percentage of duplicate identities in Employee file | 2009-02-13 | FHDA | To be done
IDM | Determine Percentage of duplicate identities in Alumni file | 2009-02-13 | FHDA | To be done
IDM | Determine Percentage of duplicate identities across Student, Employee and Alumni | 2009-02-13 | FHDA | To be done
IDM | Define Current Account creation process for Student, Employee, Alumni and Affiliates | 2009-02-13 | FHDA | To be done
IDM | Identify system of authority for affiliates | 2009-02-13 | FHDA | To be done
IDM/MIGR | Decide what subset of general entity data needs to be available for July go live | 2009-02-20 | FHDA | To be done
IDM | Decide on Identity structure (CWID, with/without prefix) to be implemented | 2009-02-20 | FHDA | To be done
IDM | Decide on Single Sign on (SSO) naming convention | 2009-02-20 | FHDA | To be done
MIGR | Obtain consensus/approval on data standards | 2009-02-20 | FHDA | To be done
MIGR | Determine when General Person Synchronization software will be required | 2009-02-20 | FHDA | To be done
IDM | Aggregate known institutional identifiers (see note below) | Tactical Workshop** | FHDA/SGHE | To be done
IDM | Identify Enterprise Identity Data Model | Tactical Workshop** | FHDA/SGHE | To be done
IDM | Align Identity Data Model to General Person Synchronization Rules | Tactical Workshop** | FHDA/SGHE | To be done
IDM | Identify legacy Roles requirements | Tactical Workshop** | FHDA/SGHE | To be done
IDM | Align Role requirements to General Person Synchronization plan for Role management | Tactical Workshop** | FHDA/SGHE | To be done
IDM | Build IAM Transitionary Plan - legacy to Banner by Module go-live as indicated on the project timeline | Tactical Workshop** | FHDA/SGHE | To be done
IDM | Determine security and access training procedures | 2009-02-27 | FHDA | To be done
LUMINIS | PROD - Install LP 4.x environment (w/ clustered Resource Tier if LP 4.3) | 2009-04-17 | SGHE | To be done
LUMINIS | PROD - Implement Banner-side Data Integration Consultation Recommendations | 2009-04-17 | FHDA/SGHE | To be done
LUMINIS | PROD - Luminis/Banner Data Integration Setup (LMG) | 2009-04-24 | SGHE | To be done
LUMINIS | PROD - Load ICGORLDI Extract into Luminis | 2009-04-24 | SGHE | To be done
LUMINIS | PROD - Luminis/Banner Middle Tier Integration | 2009-05-01 | SGHE | To be done
LUMINIS | PROD - Setup Luminis content | 2009-05-29 | FHDA | To be done
LUMINIS | PROD - Configure / Test SSO Connectors (TBD by FHDA) | 2009-05-29 | FHDA | To be done
LUMINIS | PROD - LP 4.x Technical Production Readiness Review | 2009-06-05 | SGHE | To be done
MIGR | Decide address hierarchy (enterprise-wide priority ordering of address types) | During Gen.Person Synch. Effort | FHDA | To be done
MIGR | Load person data (student and employee) from Plus to Banner | During Gen.Person Synch. Effort | FHDA | To be done
MIGR | Develop duplicate identity procedures | Tactical Workshop** | FHDA | To be done
IDM | Decide on how affiliates will be handled | Tactical Workshop** | FHDA | To be done
IDM | Test Provisioning to Luminis via UDCIdentity | Tactical Workshop** | FHDA/SGHE | To be done
IDM | Prod Install Banner Enterprise Identity Services | When LP PROD Avail. | FHDA/SGHE | To be done
IDM | Prod - Provision Luminis via UDCIdentity | When LP PROD Avail. | FHDA/SGHE | To be done
LUMINIS | Make decision regarding LP 4.2 on RHEL AS3 vs. LP 4.3 on RHEL AS4 | TBD | FHDA/SGHE | To be done
LUMINIS | FHDA Staff Attend Luminis System Administrator Training | TBD | FHDA | To be done
LUMINIS | TEST - Install LP 4.x environment (w/ clustered Resource Tier if LP 4.3) | TBD | SGHE | To be done
LUMINIS | TEST - Luminis/Banner Data Integration Setup (LMG) | TBD | SGHE | To be done
LUMINIS | TEST - Implement Banner-side Data Integration Consultation Recommendations | TBD | FHDA/SGHE | To be done
LUMINIS | TEST - Load ICGORLDI Extract into Luminis | TBD | SGHE | To be done
LUMINIS | TEST - Luminis/Banner Middle Tier Integration | TBD | SGHE | To be done
Note: These items will be addressed during the week of the workshop. Decisions made will be reflected in write-up. Items requiring additional input will be assigned as action items with due dates as to when they need to be resolved.