## IdM and Integration Plan
Task | Work | Work | Start | Finish | Resource
Foothill DeAnza Integration Plan | 594h | 594h | 2008-06-02 08:00 | 2009-08-21 17:00
Identity Management | 304h | 304h | 2009-01-26 08:00 | 2009-05-22 17:00
UDC Identity and Provisioning | 64h | 64h | 2009-01-26 08:00 | 2009-02-20 17:00
UDCP Integration Architect | 12h | 12 | 2009-01-26 08:00 | 2009-02-20 17:00 | Integration Engineer
UDCP Planning Call | 4h | 4 | 2009-01-26 08:00 | 2009-01-30 17:00 | Integration Engineer
UDCP Readiness Document from Client | 0h | 0h | 2009-01-30 08:00 | 2009-01-30 17:00
UDCP Onsite Implementation | 32h | 32 | 2009-02-02 08:00 | 2009-02-06 17:00 | Integration Engineer
UDCP Travel | 8h | 8 | 2009-02-02 08:00 | 2009-02-06 17:00 | Integration Engineer
UDCP Offsite Consulting | 6h | 6 | 2009-02-09 08:00 | 2009-02-13 17:00 | Integration Engineer
UDCP Trip Report | 2h | 2 | 2009-02-09 08:00 | 2009-02-13 17:00 | Integration Engineer
SunOne Connector Implementation | 180h | 180h | 2009-03-02 08:00 | 2009-05-08 17:00
SUNC Planning | 8h | 8 | 2009-03-02 08:00 | 2009-03-06 17:00 | Integration Engineer
SUNC Identity Oversight | 32h | 32 | 2009-03-02 08:00 | 2009-03-06 17:00 | Integration Engineer
SUNC Travel | 8h | 8 | 2009-03-09 08:00 | 2009-03-13 17:00 | Integration Engineer
SUNC Onsite Implementation | 32h | 32 | 2009-03-09 08:00 | 2009-03-13 17:00 | Integration Engineer
SUNC Testing Support | 80h | 80 | 2009-03-16 08:00 | 2009-03-27 17:00 | Integration Engineer
Identity Mangement Remote Support | 20h | 20 | 2009-03-30 08:00 | 2009-05-08 17:00 | Integration Engineer
Go-live support | 60h | 60h | 2009-05-11 08:00 | 2009-05-22 17:00
SUNC Production Migration Support | 40h | 40 | 2009-05-11 08:00 | 2009-05-22 17:00 | Integration Engineer
SUNC Production Oversight | 20h | 20 | 2009-05-11 08:00 | 2009-05-22 17:00 | Integration Engineer
Integration for eLearning | 290h | 290h | 2008-06-02 08:00 | 2009-08-21 17:00
Project Planning and Organizational Readiness | 22h | 22h | 2009-06-01 08:00 | 2009-06-26 17:00
Project Planning Activities | 12h | 12 | 2009-06-01 08:00 | 2009-06-26 17:00 | Integration Engineer
Functional Planning Conference Calls | 3h | 3 | 2009-06-01 08:00 | 2009-06-19 17:00 | Integration Engineer
Technical Planning Conference Calls | 3h | 3 | 2009-06-01 08:00 | 2009-06-19 17:00 | Integration Engineer
LDI Implementation Blueprint Review and Verification of Remote Connectivity | 4h | 4 | 2009-06-22 08:00 | 2009-06-26 17:00 | Integration Engineer
Installation, Technical Training & Installation Support | 78h | 78h | 2009-06-29 08:00 | 2009-08-07 17:00
Test System Installation (Remote) | 36h | 36 | 2009-06-29 08:00 | 2009-07-03 17:00 | Integration Engineer
Technical Training (Remote) | 8h | 8 | 2009-07-06 08:00 | 2009-07-10 17:00 | Integration Engineer
Document Test Installation (Remote) | 4h | 4 | 2009-07-06 08:00 | 2009-07-10 17:00 | Integration Engineer
Follow-Up Technical Support | 10h | 10 | 2009-06-29 08:00 | 2009-08-07 17:00 | Integration Engineer
Moodle Adapter Validation | 20h | 20 | 2009-06-29 08:00 | 2009-07-03 17:00 | Integration Engineer
Program Planning Review, Knowledge Transfer, System Verification | 50h | 50h | 2009-07-13 08:00 | 2009-08-07 17:00
Program Planning Review - On-site | 4h | 4 | 2009-07-13 08:00 | 2009-07-17 17:00 | Integration Engineer
Knowledge Transfer (Functional Training) - On-site | 12h | 12 | 2009-07-13 08:00 | 2009-07-17 17:00 | Integration Engineer
System Verification & Test; Debugging Skills - On-site | 16h | 16 | 2009-07-13 08:00 | 2009-07-17 17:00 | Integration Engineer
Travel | 8h | 8 | 2009-07-13 08:00 | 2009-07-17 17:00 | Integration Engineer
Prepare Trip Report | 2h | 2 | 2009-07-20 08:00 | 2009-07-22 12:00 | Integration Engineer
Remote Functional Support | 8h | 8 | 2009-07-13 08:00 | 2009-08-07 17:00 | Integration Engineer
Pre-Production Support | 12h | 12h | 2009-08-10 08:00 | 2009-08-21 17:00
Pre-Production Functional Support | 6h | 6 | 2009-08-10 08:00 | 2009-08-21 17:00 | Integration Engineer
Pre-Production Technical Support | 6h | 6 | 2009-08-10 08:00 | 2009-08-21 17:00 | Integration Engineer
Project Coordination and Q&A | 18h | 18h | 2009-06-01 08:00 | 2009-08-21 17:00
Project QA Activities | 8h | 8 | 2009-06-01 08:00 | 2009-08-21 17:00 | Integration Engineer
Overall Project Coordination | 10h | 10 | 2009-06-01 08:00 | 2009-08-21 17:00 | Integration Engineer
Content Based Router | 90h | 90h | 2009-07-22 13:00 | 2009-08-19 12:00
CBR Design | 16h | 16 | 2009-07-22 13:00 | 2009-07-29 12:00 | Integration Engineer
CBR Development | 40h | 40 | 2009-07-29 13:00 | 2009-08-05 12:00 | Integration Engineer
CBR Testing | 20h | 20 | 2009-08-05 13:00 | 2009-08-12 12:00 | Integration Engineer
CBR Knowledge Transfer | 14h | 14 | 2009-08-12 13:00 | 2009-08-19 12:00 | Integration Engineer
Moodle SSO Connector | 20h | 20h | 2008-06-02 08:00 | 2008-06-06 17:00
Advisory services - fixed fee nonbillable in Clarity | 20h | 20 | 2008-06-02 08:00 | 2008-06-06 17:00 | Integration Engineer