## Sheet1
Foothill-De Anza Timeline Summer Go-Live
Mon-Yr | Event
2009-07-01 | Roll of 2009 schedules to TEST
2009-08-01 | General Student, Registration Fee Assess training completed
2009-09-01 | Build Detail Codes (Acct. Rec.)
2009-10-01 | Academic History Training completed
2009-11-01 | General Person Conversion
2009-11-01 | Classroom conversion
2009-11-01 | Catalog and Schedule conversion
2009-11-01 | Mock Catalog Entered
2009-11-01 | Activate enough faculty on SIAINST for mock
2009-11-01 | Mock Schedule Entered (Test batch application load)
2009-11-01 | Mock Registration and Feed to Finance (Acct. Rec.)
2009-12-01 | 1st General Student Conversion
2009-12-01 | Test CCCApply interface
2009-12-01 | Mock Registration (Load Testing Completed)
2010-01-01 | Faculty Conversion
2010-01-01 | Faculty Load Go-Live
2010-01-01 | Catalog Go-Live
2010-01-01 | Mock Schedule Entered
2010-02-10 | Mock Registration (Test All Interfaces including Payment Gateway)
2010-03-10 | Accounts Receivable Conversion
2010-03-10 | Final General Student Conversion
2010-03-10 | General Student Go-Live
2010-03-10 | Accounts Receivable Go-Live for Summer Disbursements
2010-03-10 | Class Schedule Go-Live
2010-03-10 | Financial Aid Disbursements for Summer
2010-04-01 | Admissions Data Conversion
2010-04-01 | Admissions Go-Live
2010-04-01 | Academic History Conversion (Detailed Conversion)
2010-04-01 | Winter and Spring registration converted w/ IP grades
2010-05-01 | DSPS, EOPS, and Matriculation tracking Go-Live
2010-05-01 | Registration Go-Live
2010-05-01 | Self-Service Go-Live
July/Aug 2010 | Convert Winter and Spring Academic History
2010-08-01 | Academic History Go-Live
2010-09-01 | Continuing Education Go-live