Student Go Live Status Meeting

3-19-10

Kathleen asked all the team leaders to create/maintain list of tables they find without info built so she can follow up w/SunGard.  She distributed the consulting schedule and timelines for Go Live.  She requested specific topics/problems to forward to Xiaobin Li prior to the tech consulting Mar 23-25. Also she pointed out that a new functional consultant has been hired to work through the remaining process/set up problems.  Groups should review the calendar and let Kathleen know what weeks they want to meet with him.  Accts Rec has the week of Mar 29.

Fin Aid/CCC

- FinAid has moved into PROD--Complete

- Testing will occur over weekend--Complete

- Live CCC has been created and Banner interface set up--Complete

- Staff will create CCC apps to upload as test--Complete

- FinAid hiring a lobby person to assist with MyPortal--Complete

- Front desk and phone staff need training to assist students using MyPortal/CC--Partially Complete

- Residency workflow needs to be addressed--In Progress

- Discussed Banner dupes and assigning staff to review and clean up on regular basis	In Progress

- BOGs still not working on FH side in TRNG--Complete

NEW ISSUES STILL UNRESOLVED:

  - SGASTDN program/priority/effective term issues related to Pell awarding

  - Concurrent enrollment vs transfer enrollment during an aid year

  - Possible consortium solutions for concurrent/transfer students

Assessment

- Assessment has been working with Jerrick to perfect the Accuplacer upload; seems to be working well

- Reviewed where test scores/prereqs should be loaded - catalog or schedule level; prereqs at section level work for registration.  Jerrick has already populated SCAPREQ and SSAPREQ with the prerequisite information on SI's 12R and 131 screens

- PDF or other crosswalk to be linked to student portal so raw scores = placement levels

- Discussed the process of high school assessment and how IDs would be collected so upload could occur- sent info to DA Outreach/Shawna to follow up w/FH Outreach

- Discussed that prereq checking between spring in progress SIS courses and summer Banner registration would likely have glitches or be suspended.  There is a process that A&R will have to coordinate with Assessment after running SHRROL to determine if students have passed prereqs and then need to be dropped from next level.

- Shawna to check with Tita to ensure that their set up is OK at FH

Accts Receivable

- Need to set up 1.)sleep/wake processes in Banner by cashiering office 2.) other processes by ETS and test them--Pending

- Need FOAPs created and checked by Finance--Pending

- Problem with info being updated being superseded by old tables--Complete

- Detail codes look good but still need review (will work on this after finishing the Scholarship detail code)--Pending

- Web payment gateway needs install and testing--Pending

- Billing history (need to meet with Hector, Martin and Sheila), will probably move bal forward.  Unresolved how much billing history to move. 1098t is only reason (agree to bring the due amount only) --Complete in theory - need to move data

- 3rd Party contract (needs to work with Shawna)--Pending

- Exemptions are complete (new idea from Antonio that we may able to attach multiple detail codes to 1 exemption code) ??

- Material fees need to be built at the section level.  At DA we need to determine who is doing this; FH Registrar is building the matl fees.  Jerrick seeing if a script can be develop from SIS to Banner.--Pending

- Evisions - need to develop nice looking invoices/forms (work with Matt)--Pending. Need set up time with Matt.

- Installment plan (1. IP/TP; 2. for FA book loan)--Pending

- Need to set up auto billing notification in Luminous--Pending.

- Still no info about Credentials parking process/interface from Police

- Discussed running 1098T for 09-10 from SIS/Banner

- Refund process, drop for nonpayment policy/procedure, and concurrently enrolled student processing TBD!!

NEW:

- Need to decide 1 cut off date or have the SI and Banner up during the transition period.  Antonio recommends keeping SIS up through spring and feeding to Finance periodically.

- Also look at having a mandatory PAY NOW button on AR side and then offer auto enrollment into installment plan.  AR/Finance to review third party vendors offering this service.

Academic History

- Cleaned up STVMAJR/SMAPRL/SOACUR for CCC interface

- Creating new codes for FinAid ineligible programs

- Working on Acad History migration and checking GPA, etc

- Working on transfer institution codes in Banner for Acad History; Jerrick to see about a script to upload SIS codes

- Discussed how much general person info to bring over and whether we have staff available for clean up

General Person Migration

- This work continues in both SIS and PROD

- Shelley at FH to compare with Nancy Charnoski regarding status

- Banner creates dupes; need to assign staff to clean up on ongoing basis

- Jim Clow has created an error report in Banner to locate dupes,

- Still some issues around SSN in SIS and no SSN in Banner

Registration/Grades

- Add codes still aren’t working, Dottie not sure why - Pending

- DTR - plan to run in SIS for continuing students for summer and then move to Banner somehow--Pending

- DTR - need to develop script for new applicants to get DTR for summer/fall Pending

- Not sure how waitlists work and how students are notified-Pending

- Need to add two codes to STVRSTS (Kathleen to do) Complete

- Still unclear of how we will send out general emails; probably learn how to use the tool in Luminis and/or Webteam Pending

- Add/drop for nonstandard and term spanning classes needs testing. Pending

- Need to work with ETS on print jobs such as Add codes and transcripts (set up of printers using Banner) -Pending

- Discussed the process for rolling grades then running the report that checks for prereq completion; need to coord with Assessment -Pending

- Need PDF or other verification of grades for audit, etc (Checking w/Luminis team) Pending

- Need to identify reports for Andrew and how this info will be retrieved (through ETS, desktop report or ?) --Pending

Hershey Migration

- Contract go ahead, but reduced from 200-100 hours; target June 1.

- Need to know what tech and A&R support will be required

- FH needs to work with Louis about how to move their files (not in Hershey)

- Need to determine when we will suspend all scanning into Hershey

- Need to work with ETS to identify workstations that will need scanners for BDMS

EDI

- Pat working with Credentials; interface ready.  Target: May or so

- Need to work w/Matt on Evisions and the transcript print form

- Heard that screen scrapes and such won’t work with Form Fusion (evisions), need to check with Credentials about forms and how other Banner schools do this

- Need to find out from Credentials if we can have Credentials up with SIS (spring) and Banner (summer) simultaneously

International Students

- ISP offices to use their INB apps to manually enter international data

- Developing process for handling renewal of PIN for International students in the absence of SSN (Is DA ISP aware of this?)

- CIP codes need to be cross-walked to SEVIS codes for STVMAJR (Lourdes/Jerrick to work on this)

- ISP offices will review the SEVIS codes for OK to FSAtlas

Counseling

- No report