## Weekly Events Calendar
Week of | Session | Area | Consultant | Session Type | Suggested FHDA Participants | Comments | Changes
2010-01-11 | DW - Focus call to review timelines, implementation methodology and documents--Scheduled for 1/15/2010 (invites sent) | ST DegreeWorks | M. Nichols | Conference Call | Degree Audit | DegreeWorks Planning/Focus Call. Primary FHDA contact Kathleen Moberg. Participants have been invited. | Updated 1/13/2010
2010-02-15 | EDW - Conduct Testing Session 1 CANCELED | IA EDW |  | System Testing | Reporting Technical Team |  | CANCELED 1/13/2010
2010-03-08 | ST Strategic Technical Support | ST Tech | X. Li | Technical Consulting | Technical Team |  | Added 2/19/2010
2010-03-15 | BDMS Hershey Conversion Week of March 15, 2010 | BDMS Tech Conv | L. Chen | Technical Consulting | Imaging/Hershey | Remote (16 hour) Planning Session | Added 3/7/2010
2010-03-15 | ST Strategic/Advisory Consulting | ST Func | A. Trepesowsky | Functional Consulting | Student Core Team | Note: Student AR Summit 3/15; Student Assessment Summit 3/18 | Added 2/19/2010
2010-03-15 | ST Strategic Technical Support | ST Tech | X. Li | Technical Consulting | Technical Team | Note: Student AR Summit 3/15; Student Assessment Summit 3/18 | Added 2/25/2010
2010-03-22 | Mini Summits for Student/Reg and Luminis/Student | Student
2010-03-22 | ST Strategic Technical Support | ST Tech | X. Li | Technical Consulting | Technical Team |  | Added 2/19/2010
2010-03-29 | ST Strategic/Advisory Consulting | ST Func | A. Trepesowsky | Functional Consulting | Student Core Team |  | Added 2/19/2010
2010-04-01 | Last week to work in TST 8 | Student
2010-04-05 | Student Move to TRNG 8 - until May 1 | Student | Roza
2010-04-05 | ST Strategic Technical Support | ST Tech | X. Li | Technical Consulting | Technical Team |  | Added 2/19/2010
2010-04-12 | Move Academic History into PROD | Student | J Woo
2010-04-19 | ST Strategic/Advisory Consulting | ST Func | A. Trepesowsky | Functional Consulting | Student Core Team |  | Added 2/19/2010
APRIL | Review and Testing of All Student Rulesin TRNG8
2010-04-05 | Test and review Fac/Stu SS and document | Luminis/ST |  |  | Luminis/Stu Teams
2010-04-19 | ST Strategic Technical Support (Remote) | ST Tech | X. Li | Technical Consulting | Technical Team | Remote | Added 2/19/2010
2010-04-26 | Move Accts Rec balance forward to TRNG 8 | Accts Rec
2010-04-26 | BDMS Hershey Conversion Week of April 26, 2010 | BDMS Tech Conv | L. Chen | Technical Consulting | Imaging/Hershey | Remote (20 hour) Session | Added 3/7/2010
2010-04-30 | DTR scripts must be complete; ready for PROD May 10 | Registration | Trepesowsky |  | Woo/Reg team
2010-04-30 | Accuplacer Upload must be correct and ready for PROD | Assess | Trepesowsky
2010-04-30 | Form fusion work on invoice format | Accts Rec |  |  | Matt/Accts Rec
2010-04-30 | Tentative date for summer schedule to web
2010-05-03 | Student Move to PRODN Testing through May 17 | ST | Roza | Tech Function
2010-05-03 | ST Advisory Week 11 | ST Func | D. Marron | Functional Consulting | Student Core Team
2010-05-03 | ST Strategic/Advisory Consulting | ST Func | A. Trepesowsky | Functional Consulting | Student Core Team |  | Added 2/19/2010
2010-05-03 | BDMS Hershey Conversion Week of May 3, 2010 | BDMS Tech Conv | L. Chen | Technical Consulting | Imaging/Hershey | 40 hours | Added 3/7/2010
2010-05-03 | Banner/Creden pkg interface installed/tested by now | Accts Rec |  |  | Police/Accts Rec/Tech
2010-05-03 | Payment Gateway s/b installed and tested by now | Accts Rec | Touchnet |  | Tech Team/Acct Rec
2010-05-03 | DTR to PRODN w/msg to students?? |  | J Woo |  | Luminis/Stu Teams
2010-05-10 | Train front counter staff for summer reg, etc.
2010-05-10 | Email address/set up for auto waitlist msg needed |  | ETS
2010-05-10 | BDMS Hershey Conversion Week of May 10, 2010 | BDMS Tech Conv | L. Chen | Technical Consulting | Imaging/Hershey | 40 hours | Added 3/7/2010
2010-05-17 | Student Move to PROD - GO LIVE May 21 | Student | Roza | Tech Function
2010-05-17 | Activate the Pilot Couns 100 courses for May 22 reg | ST/Instr Support |  | Functional Consulting | Instruc Support/ST
2010-05-17 | BDMS Hershey Conversion Week of May 17, 2010 | BDMS Tech Conv | L. Chen | Technical Consulting | Imaging/Hershey | 40 hours | Added 3/7/2010
2010-05-24 | ST Strategic/Advisory Consulting | ST Func | A. Trepesowsky | Functional Consulting | Student Core Team |  | Added 2/19/2010
2010-06-07 | Form fusion work on transcript format | ST Func |  |  | Matt R/Stu Team
2010-06-07 | Assess summer add code/roster, etc process
2010-06-07 | ST Advisory Week 12 | ST Func | D. Marron | Functional Consulting | Student Core Team
2010-06-14 | ST Strategic/Advisory Consulting | ST Func | A. Trepesowsky | Functional Consulting | Student Core Team |  | Added 2/19/2010
2010-06-21 | Notify Summer Faculty of New Processes | A&R |  |  | A&R, Fac, Couns,Div Admins
2010-06-23 | Print summer add codes, rosters if needed |  |  |  | A&R
2010-06-28 | ST Strategic/Advisory Consulting | ST Func | A. Trepesowsky | Functional Consulting | Student Core Team |  | Added 2/19/2010
2010-07-05 | Test Credentials/Banner interface in PRODN | ST Func
2010-07-05 |  | OPEN
2010-07-12 | ST Strategic/Advisory Consulting | ST Func | A. Trepesowsky | Functional Consulting | Student Core Team |  | Added 2/19/2010
2010-07-12 | Clearinghouse Upload from Banner (summer enrol) |  | FinAid/AD
2010-08-02 | Make transition from Credentials SIS to Banner (trans) | ST Func | Woo/Crede
2010-08-09 | Begin Degree Works training | DegreeWks |  |  | Evaluators
2010-08-19 | Credentials from Banner Live for summer term | ST Func | Woo/Crede
2010-08-20 | Clearinghouse upload from SIS/spring degrees | ST Func | Eval