## Weekly Events Calendar
Week of | Session | Area | Consultant | Session Type | Suggested FHDA Participants | Comments | Changes
2008-09-01 | Technical Architecture Review | TN | H. Classe | Assessment | Senior IT Staff | Admin's as necessary
2008-09-15 | Develop and Deliver Technical Architecture Document, Follow-up | TN | H. Classe | Conference Call | Senior IT Staff
2008-09-15 | Finance BPA Consultant Planning | FI | L. Talbert | Conference Call | Finance Core Team
2008-09-15 | HR BPA Consultant Planning Call | HR | L. Talbert | Conference Call | HR Core Team
2008-09-22 | TN Banner Pre-Install Verification | TN | H. Classe | Remote | IT Core Team | ad hoc coordination
2008-09-22 | Luminis Technical Planning Workshop | LM | R. Wright | Technical Consulting | Luminis Technical Team
2008-09-29 | TN Banner Seed Install (Remote) | TN | T. Schmidt | Remote | IT Core Team | ad hoc coordination
2008-09-29 | Luminis Project Kickoff | LM | A. Eagleston | Org. Consulting | Luminis Project Team Stakeholders | Functional Areas; Designated Times
2008-09-29 | Luminis Technical blueprint document creation | LM | R. Wright | Remote | Luminis Technical Team | ad hoc questions
2008-10-06 | TN Banner App Server Install (Remote) | TN | R. Teschner | Remote | IT Core Team | ad hoc coordination
2008-10-06 | Integration Assessment Planning Conference Call | EA | S. Johnson | Conference Call | IT Core Team
2008-10-06 | Student BPA Consultant Planning | ST | J. Tisdale | Conference Call | Student Core Team
2008-10-06 | Financial Aid BPA Consultant Planning | FA | J. Tisdale | Conference Call | Financial Aid Core Team
2008-10-06 | FI Finance Project Planning | FI | L. Talbert | Conference Call | Finance Team Leader | Key Finance Team Members
2008-10-06 | Luminis Technical blueprint document creation | LM | R. Wright | Remote | Luminis Technical Team | ad hoc questions
2008-10-13 | TN Banner Self Service and CALB Install (Remote) | TN | R. Teschner | Remote | IT Core Team | ad hoc coordination
2008-10-13 | Prepare DRAFT Application Matrix | EA | S. Johnson | Remote | IT Core Team | ad hoc questions
2008-10-13 | Luminis OIG (Organizational Information Gathering) | LM | J. Handa | Org. Consulting | Luminis Core Team |  | Now 11/17
2008-10-20 | TN Post-installation Review (Onsite or Remote) | TN | R. Teschner | Technical Consulting | IT Core Team | Knowledge Sharing
2008-10-20 | HR BPA - On-Site | HR | L. Talbert | Analysis | HR Core Team
2008-10-20 | Migration Assessment and Planning - Conversion Plan building | EA | B. Braun | Conference Calls | EIS Core Team | Functional Areas; Designated Times
2008-10-20 | Prepare DRAFT Application Matrix | EA | S. Johnson | Remote | IT Core Team | ad hoc questions
2008-10-27 | Data Migration Toolkit Installation (may be moved to later date, TBD) | TN | R. Teschner | Remote | IT Core (Apps) Team | ad hoc questions
2008-10-27 | Banner General & Security training BT 102 | TN | G. Hunt | Technical Training | IT EIS Team | All Tech's on Project
2008-10-27 | FI Kickoff, Finance Overview and Navigation, First COA Training | FI | J. Langlois | Functional Training | Finance Team | First Finance Training Session
2008-10-27 | HR Project Planning Session | HR | J. Greer | Conference Call | HR Core Team
2008-11-03 | Luminis Remote Platform Install | LM | R. Wright | Remote | Luminis Technical Team | ad hoc questions
2008-11-03 | Integration Assessment | EA | S. Johnson | Assessment | IT Core Team | Functional Areas; Designated Times
2008-11-03 | Sun IdM Services - Planning Session (11/5 and 11/6) | EA | D. Cody | Planning | IT Core Team
2008-11-03 | HR BPA Deliverable Write-up | HR | L. Talbert | Remote | HR Team Leader | ad hoc questions
2008-11-10 | Luminis Parallel Deployment | LM | R. Wright | Remote | Luminis Technical Team | ad hoc questions
2008-11-10 | Finance BPA - On-site | FI | L. Talbert | Analysis | Finance Team
2008-11-10 | HR Kickoff, HR Overview, Intro to General, Bio/Demo, Employee Class, Position | HR | J. Summers | Functional Training | HR Team | First HR Training Session
2008-11-17 | Luminis ERP Integration, Configure Channels for Banner | LM | R. Wright | Remote | Luminis Technical Team | ad hoc questions
2008-11-17 | ST Project Planning | ST | D. Marron | Conference Call | Student Core Team
2008-11-17 | Finance BPA Deliverable Write-up | FI | J. Tisdale | Remote | Finance Team Leader | ad hoc questions
2008-11-17 | Luminis Organization Information Gathering (11/19) | LM | J. Handa | Org. Consulting | Luminis Core Team |  | Was 10/13
2008-11-17 | Luminis Project Planning and Review(11/20) | LM | R. Wright | Org. Consulting | Luminis Core Team
2008-11-17 | Information Access Strategy | IA | R. Ameen | Assessment | Reporting Team, EIS Core Team | Functional Areas; Designated Times
2008-11-24 | FI Progress Assessment - REMOTE | FI | G. Houck | Conference Call | Finance Team Leader |  | Now 12/8
2008-11-24 | ODS Planning Call, Kickoff Meeting (may move to December) | IA | R. Williams | Conference Call | Reporting Team, EIS Core Team |  | Now 12/15
2008-11-24 | ODS Technical Implementation Planning (may move to December) | IA | R. Williams | Conference Call | Reporting Team | Rptg. Leaders, Technical Team | Now 12/15
2008-12-01 | Student BPA - On-site | ST | J. Tisdale | Analysis | Student Team | Recommend 15 - 18 Participants
2008-12-01 | Finance BPA Delverable Write-up | FI | J. Tisdale | Remote | Finance Team Leader | ad hoc questions
2008-12-01 | FI Initial Tech Training | FI | D. Shah | Technical Training | Finance Technical Team
2008-12-01 | FA Project Planning | FA | C. Linsley | Conference Call | Financial Aid Core Team
2008-12-08 | FI Second Chart of Accounts Training | FI | J. Valori | Functional Training | Finance Team
2008-12-08 | FI Progress Assessment - REMOTE | FI | G. Houck | Conference Call | Finance Team Leader | Will be on 12/12 | Was 11/24
2008-12-08 | HR Foundation Basics and Employment Administration | HR | J. Greer | Functional Training | HR Team
2008-12-08 | Financial Aid BPA - On-Site | FA | J. Tisdale | Analysis | Financial Aid Team
2008-12-08 | Student BPA Delverable Write-up | ST | J. Tisdale | Remote | Student Team Leaders | ad hoc questions
2008-12-15 | ODS Planning Call, Kickoff Meeting (may move to 12/15) | IA | R. Williams | Conference Call | Reporting Team, EIS Core Team |  | Was 11/24
2008-12-15 | ODS Technical Implementation Planning (may move to 12/15) | IA | R. Williams | Conference Call | Reporting Team | Rptg. Leaders, Technical Team | Was 11/24
2008-12-15 | FI Procuring Goods and Services | FI | J. Langlois | Functional Training | Finance Team
2008-12-15 | Financial Aid BPA Deliverable Write-up | FA | J. Tisdale | Remote | Financial Aid Team Leader | ad hoc questions
2008-12-15 | Luminis Content Planning | LM | D. Douglas | Org. Consulting | Luminis Core Team
2008-12-15 | OR101 - Introduction to Oracle | TN | S. Stutheit | Technical Training | IT Team
2009-12-22
2009-12-29
2009-01-05 | FI Accounts Payable, Vendor Payments, Bank Reconciliation | FI | J. Langlois | Functional Training | Finance Team
2009-01-05 | HR Compensation, Job and Leave Administration | HR | J. Greer | Functional Training | HR Team
2009-01-12 | HR Progress Assessment 1 | HR |  | Conference Call | HR Team Leader |  | Cancelled
2009-01-12 | Luminis Organizational Planning | LM |  | Org. Consulting | Luminis Core Team |  | Now 1/26
2009-01-12 | OR102 - PL/SQL and Database Objects | TN | R. Watkins | Technical Training | IT Team |  | Added
2009-01-19 | FI Research and Proposals | FI | J. Langlois | Functional Training | Finance Team
2009-01-19 | FI Progress Assessment - REMOTE | FI | G. Houck | Conference Call | Finance Team Leader | Will be on 1/23 | Added
2009-01-19 | ST Implementation Overview, General System and General Person | ST | D. Marron | Functional Training | Student Team | First Student Training Session
2009-01-19 | Luminis Data Integration Consultation - On-Site | LM | K. Stone | Technical Consulting | Luminis Technical Team
2009-01-19 | ODS, ETL, Admin System Install and Data Load - Remote (Tentative) | IA | R. Williams | Remote | Reporting Technical Team | ad hoc questions
2009-01-26 | FI Advisory Week 2 - Conversion Planning for Vendor File (Tentative) | FI | J. Langlois | Functional Consulting | Finance Team | Purchasing, Finance Technical
2009-01-26 | HR Benefits, Deductions and Tax Administration | HR | J. Summers | Functional Training | HR Team
2009-01-26 | FA Record Creation, Dataload, Req Tracking | FA | C. Linsley | Functional Training | Financial Aid Team | 1st Financial Aid Training Session
2009-01-26 | Luminis Organizational Planning | LM | D. Douglas | Org. Consulting | Luminis Core Team |  | Was 1/12
2009-02-02 | FI Research Billing | FI |  | Functional Training | Finance Team |  | Defer to later
2009-02-02 | HR Tech Training | HR | L. Heineman | Technical Training | HR Technical Team
2009-02-02 | ODS - Conduct technical training (Tentative) | IA |  | Technical Training | Reporting Technical Team |  | Now 3/2
2009-02-02 | UDCP Implementation | TN | B. DeMillion | Installation | System Administrators |  | Added
2009-02-02 | IAM Workshop Planning Conference Call | TN | D. Cody | Conference Call | System Administrators |  | Added
2009-02-09 | Training Needs Assessment - Finance | TR | G. Burbank | Assessment | Finance, HR Core Teams
2009-02-09 | ST Recruitment, Admissions, Communications Plans | ST | D. Marron | Functional Training | Student Team
2009-02-09 | Data Migration Toolkit Training | TN | D. Jones | Technical Consulting | IT Core Team
2009-02-09 | Luminis Content Administrator Training | LM | D. Douglas | CAT Training | Luminis Core Team | Content Administrator Focus | Was 2/16
2009-02-16 | FI Consulting Visit 1 - Validation of Procedures, Rule and Table Support | FI | A. Fazul | Functional Consulting | Finance Team
2009-02-16 | ST Catalog/Schedule, Loc Mgmt & Faculty Crossover | ST | D. Marron | Functional Training | Student Team | Instructional Support Focus
2009-02-16 | Tactical IAM Workshop | TN | D. Cody | Technical Training | DBA, System Adminstrators |  | Added
2009-02-16 | Luminis Content Administrator Training | LM |  | CAT Training | Luminis Core Team | Content Administrator Focus | Now 2/9
2009-02-23 | FI Banner Bridges to Finance | FI | D. Martinez | Technical Training | Finance Technical Team |  | Added
2009-02-23 | ST Initial Student Tech Training | ST | D. Jones | Technical Training | Student Technical Team
2009-02-23 | FI Progress Assessment - REMOTE | FI | G. Houck | Conference Call | Finance Team Leader | May need to move out
2009-02-23 | FA Needs Analysis, ISIR Correction Processing | FA | C. Linsley | Functional Training | Financial Aid Team
2009-02-23 | BT101 - Introduction to Banner Administration | TN | C. Lin | Technical Training | ETS DBA's, Sys Admin's |  | Was 2/16
2009-03-02 | HR Payroll Administration | HR | D. Sykora | Functional Training | HR Team
2009-03-02 | Training Needs Assessment - Student, Financial Aid and Advancement (may move to later) | TR |  | Assessment | EIS Core Team | Student, Financial Aid, Advancement | Delayed
2009-03-02 | ODS - Conduct technical training (Moved from 2/2/09) | IA | R. Williams | Technical Training | Reporting Technical Team |  | Was 2/2
2009-03-09 | FI Rules, Security, and Approvals | FI | A. Fazul | Functional Training | Finance Team
2009-03-09 | Banner Bridges to Finance - Remote Analysis | FI | D. Martinez | Remote | Finance Techncial Team | ad hoc questions | Added
2009-03-09 | ST Consulting - General Person, Recruiting and Admissions | ST | D. Marron | Functional Consulting | Student Core Team
2009-03-09 | Luminis Test Platform Installation | LM |  | Remote | Luminis Technical Team |  | Delayed
2009-03-16 | FA PopSel, Batch Posting, Applicant Budgeting | FA | C. Linsley | Functional Training | Financial Aid Team
2009-03-16 | Conduct ODS functional training (Finance) | FI | S. Shaw | Functional Training | Finance Technical & Reporting Team | Especially those working on reports
2009-03-16 | Luminis ERP Integration - Test | LM |  | Remote | Luminis Technical Team | ad hoc questions | Delayed
2009-03-16 | Student Data Mapping Session | ST | D. Jones | Technical Consulting | Student Technical Team
2009-03-16 | ST Advisory Week 2 | ST | D. Marron | Functional Consulting | Student Core Team | Was in plan; split to second line | Postponed
2009-03-23 | FI Purchasing Card and Self Service Training | FI | J. Langlois | Functional Training | Finance Team | Wed - Fri
2009-03-23 | FA Consulting Visit 1 - topics from training 1, 2 & 3 | FA | C. Linsley | Functional Consulting | Financial Aid Core Team
2009-03-23 | HR Data Mapping & Intermediate Bridges | HR | L. Heineman | Technical Consulting | HR Technical Team
2009-03-23 | General Person Synchronization Consulting | TN | D. Gilmore | Technical Consulting | IT Team | General Person Migration Team | Added
2009-03-23 | Luminis Configure Channels for Banner - Test | LM |  | Remote | Luminis Technical Team |  | Delayed
2009-03-30 | ST Letter Generation, Population Selection, Reporting and OA views | ST | D. Marron | Functional Training | Student Team
2009-04-06 | Luminis Load Performance Testing Planning Call | LM | K. Goethe | Conference Call | Luminis Technical Team
2009-04-06 | Web Programming - REMOTE | TN | J. Boivin | Technical Training | IT Team | SSB Focus
2009-04-06 | Custom Materials Workshop (Needs to be scheduled) | TR |  | Train the Trainer | Staff responsible for preparing training materials |  | See Note
2009-04-13 | FI Finance Interfaces and Internal Vendor Load | FI | J. Langlois | Functional Training | Finance Team
2009-04-13 | FI Banner Bridges to Finance - Week 3 On-site | FI | D, Martinez | Technical Consulting | Finance Technical Team |  | Added
2009-04-13 | HR General Consulting | HR | D. Sykora | Functional Consulting | HR Core Team
2009-04-13 | SSO for Moodle Consulting | TN |  | Technical Training | IT Team | Integration Focus | Postponed
2009-04-20 | FA Initial Tech Training | FA | K. Whitelaw | Technical Training | Financial Aid Technical Team
2009-04-20 | HR Advisory Week 2 | HR |  | Functional Consulting | HR Core Team |  | Postponed
2009-04-20 | Portal Usage Emulation Scripting | LM | K. Goethe | Remote | Luminis Technical Team | ad hoc questions | now 4/27
2009-04-27 | FI Self Service Functional Training | FI | J. Langlois | Functional Training | Finance Team |  | now 3/23
2009-04-27 | ST Advisory Week 3 | ST | D. Marron | Functional Consulting | Student Core Team
2009-04-27 | Banner Student Support Session for General Person, General Student | ST | D. Jones | Technical Consulting | Student Technical Team |  | Postponed; Now 5/18
2009-04-27 | FA Advisory Week 2 (may move from 5/18) | FA |  |  |  |  | Proposed New
2009-04-27 | FA Milestone Review - REMOTE | FA |  | Conference Call | Financial Aid Team Leader
2009-04-27 | Portal Usage Emulation Scripting | LM | K. Goethe | Remote | Luminis Technical Team | ad hoc questions | Was 4/27
2009-04-27 | Repoint Luminis from Banner TEST to PPRD | LM | R. Wright | Remote | Luminis Technical Team | ad hoc questions | Added
2009-05-04 | HR and Finance Interfaces (5/5) HR, Finance General Consulting (5/6 and 5/7) | HR | J. Greer J. Langlois | Functional Consulting | HR, Finance Teams | Tuesday - Joint HR/Finance Wed, Thurs - General Consulting
2009-05-04 | ST Self Service - Prospect and Admissions | ST |  | Functional Training | Student Team |  | Now 5/25
2009-05-04 | Luminis - Conduct Load Testing | LM |  | Remote | Luminis Technical Team |  | Now 5/11
2009-05-11 | FI Non Student Accounts Receivable and Consulting | FI | J. Langlois | Functional Consulting | Finance Team
2009-05-11 | General Person Synchronization Testing | TN | D. Gilmore | Technical Consulting | IT Team | General Person Migration Team | Added
2009-05-11 | ODS Sign off and Post Implementation Follow-up | IA | R. Williams | Conference Call | Reporting Team
2009-05-11 | Luminis - Conduct Load Testing (Tentative) | LM | K. Goethe | Remote | Luminis Technical Team |  | Was 5/4
2009-05-18 | HR Advisory Consulting | HR |  | Functional Training | HR Core Teams |  | Now 5/25
2009-05-18 | Banner Student Support Session for General Person, General Student | ST | D. Jones | Technical Consulting | Student Technical Team |  | Rescheduled; Was 4/27
2009-05-18 | Financial Aid Data Mapping Session | FA | K. Whitelaw | Technical Consulting | Financial Aid Tech Team | Fin Aid Technical Team
2009-05-18 | FA Advisory Week 2 (moved to 4/27) | FA | C. Linsley | Functional Consulting | Financial Aid Core Team | Fin Aid Core Team | See Note
2009-05-18 | Luminis - Conduct Load Testing (Tentative) | LM | K. Goethe | Remote | Luminis Technical Team |  | Was 5/11
2009-05-18 | Luminis - Review Load Testing Results | LM | K. Goethe | Conference Call | Luminis Technical Team |  | Now 5/25
2009-05-25 | FI Banner Finance Technical Support | FI | D. Martinez | Technical Consulting | Finance Technical Team | Verify PROD Environment
2009-05-25 | Banner Human Resources Support Session for General Person & Employee Migration | HR | L. Heineman | Technical Consulting | HR Technical Team
2009-05-25 | HR Advisory Consulting - MIS and STRS/PERS | HR | J. Monfette | Functional Consulting | HR Core Team |  | Was 5/18
2009-05-25 | ST Faculty Load, Location, Events Management | ST | D. Marron | Functional Training | Student Team | See next entry for topics to be covered | Now re-purposed
2009-05-25 | ST Self Service - Prospect and Admissions | ST | D. Marron | Functional Training | Student Team |  | was 5/4
2009-05-25 | Luminis - Review Load Testing Results | LM | K. Goethe | Conference Call | Luminis Technical Team |  | Was 5/18
2009-06-01 | FI Consulting Visit 2 - Transition Strategy and Planning - Pre Go Live | FI | A. Fazul | Functional Consulting | Finance Core Team |  | Cancelled
2009-06-01 | FI Banner Finance Technical Support | FI | D. Martinez | Technical Consulting | Finance Technical Team |  | Added
2009-06-01 | HR Payroll Administration II (was Windstar) | HR | J. Greer | Functional Consulting | HR Core Team |  | Topic Changed
2009-06-01 | ST Progress Assessment 1 - REMOTE | ST | TBD | Conference Call | Student Team Leaders
2009-06-01 | FA Funds Management, Packaging, Disbursement, BOG Waivers | FA | C. Linsley | Functional Training | Financial Aid Team |  | Was 6/8
2009-06-01 | Repoint Luminis from Banner PPRD to PROD Repoint Luminis UDC Data/Resource Integration from Banner PPRD to PROD | LM | R. Wright | Remote | Luminis Technical Team |  | Added
2009-06-01 | LDIS Planning Calls | LM |  | Conference Calls | Luminis Technical Team | LMS Data Integration Focus | Was 7/6
2009-06-01 | Moodle SSO Connector Advisory Services (Tentative) | LM |  | Conference Calls | Integration Team |  | Added
2009-06-08 | FA Funds Management, Packaging, Disbursement, BOG Waivers | FA | C. Linsley | Functional Training | Financial Aid Team |  | Now 6/1
2009-06-08 | FI Go-Live Center - REMOTE | FI |  | Remote | Finance Team |  | Cancelled
2009-06-08 | FI Advisory Week 3 - Interfaces Follow-up | FI | J. Langlois | Functional Consulting | Finance Core Team
2009-06-08 | ODS functional training (Human Resources) | HR |  | Functional Training | HR Technical & Reporting Team | Especially those working on reports | Now 7/27
2009-06-08 | HR Progress Assessment - REMOTE | HR | TBD | Conference Call | HR Team Leader
2009-06-08 | Training Needs Assessment - HR (Will be moved to August/September, pending HR plan adjustments) | TR | G.Burbank | Conference Calls | HR Core Team |  | See Note
2009-06-15 | FI Advisory Week 4 | FI | J. Langlois | Functional Consulting | Finance Core Team
2009-06-15 | Human Resources Support Session for Position & Jobs Migration | HR | L. Heineman | Technical Training | HR Technical Team
2009-06-15 | ST Consulting 2 - Catalog, Schedule, Faculty Load and Location Mgt crossover | ST | D. Marron | Functional Training | Student Team
2009-06-15 | Luminis Production Readiness Support Off-Site Consulting | LM | D. Douglas | Remote | Luminis Technical Team
2009-06-22 | HR Testing using Test 100 Population | HR | J. Greer | Functional Training | HR Team
2009-06-22 | EDW - Planning Meetings (May not be needed) | IA | R. Williams | Conference Calls | Reporting Team, IT Core Team |  | See Note
2009-06-22 | Verify EDW Server Ready (May not be needed) | IA | R. Williams | Technical Activity | IT Team (Reporting) |  | See Note
2009-06-22 | LDIS - Review DRAFT project schedule | LM |  | Remote | Luminis Technical Team | LMS Data Integration Focus | Was 7/13
2009-06-29 | FI Go-Live | FI |  | Milestone | Finance Team
2009-06-29 | FI Go-Live Center - REMOTE | FI |  | Remote | Finance Team |  | Cancelled
2009-06-29 | FA R2T4, Student Employment, Common Functions, Data Logging, SAP | FA | C. Linsley | Functional Training | Financial Aid Team
2009-06-29 | Luminis Production Platform Certification (may not be needed) | LM | D. Douglas | Technical Consulting | Luminis Technical Team | Finance User Focus
2009-06-29 | LDIS - Test System Installation (Remote) | LM |  | Remote | Luminis Technical Team | LMS Data Integration Focus | Was 7/20
2009-07-06 | FI Go-Live Center - REMOTE | FI |  | Remote | Finance Team |  | Cancelled
2009-07-06 | Human Resources Support Session for Benefits & Deductions Migration | HR | L. Heineman | Technical Consulting | HR Technical Team
2009-07-06 | LDIS Planning Calls | LM |  | Conference Calls | Luminis Technical Team | LMS Data Integration Focus | Now 6/1
2009-07-06 | Training Needs Assessment - Student, Financial Aid (Will be moved to September/October) | TR | G.Burbank | Conference Calls | Student, Fin Aid Core Team |  | See Note
2009-07-06 | LDIS - Technical Training (Remote) | LM |  | Remote | Luminis Technical Team | LMS Data Integration Focus | Was 7/27
2009-07-13 | FI Go-Live Center - REMOTE | FI |  | Remote | Finance Team |  | Cancelled
2009-07-13 | ST Advisory Week 4 | ST | D. Marron | Functional Consulting | Student Core Team
2009-07-13 | FA Consulting Visit 2 - topics from training 4 & 5 | FA | C. Linsley | Functional Training | Financial Aid Core Team
2009-07-13 | EDW Install (Done in January) | IA |  | Remote | Reporting Technical Team |  | See Note
2009-07-13 | LDIS - Review DRAFT project schedule | LM |  | Remote | Luminis Technical Team | LMS Data Integration Focus | Now 6/22
2009-07-13 | LDIS - System Verification & Test; Debugging Skills - On-site | LM |  | Functional Training | Luminis Technical Team | LMS Data Integration Focus | Was 8/3
2009-07-13 | LDIS - Knowledge Transfer (Functional Training) - On-site | LM |  | Functional Training | Luminis Technical Team | LMS Data Integration Focus | Was 8/3
2009-07-20 | FI Go-Live Center - REMOTE | FI |  | Remote | Finance Team |  | Cancelled
2009-07-20 | HR Topics to be determined | HR | J. Greer | Functional Training | HR Team |  | Topic changed
2009-07-20 | ST Consulting and Managing International Students | ST | D. Marron | Functional Training | Student Team | International Students Focus
2009-07-20 | FA Milestone Review - REMOTE | FA | C. Marcotte | Conference Call | Financial Aid Team Leader
2009-07-20 | LDIS - Test System Installation (Remote) | LM |  | Remote | Luminis Technical Team | LMS Data Integration Focus | Now 6/29
2009-07-20 | Content Based Router Design | TN |  | Technical Consulting | Integration Team |  | Added
2009-07-27 | FI Go-Live Center - REMOTE | FI |  | Remote | Finance Team |  | Cancelled
2009-07-27 | FI Advisory Week 5 | FI | J. Langlois | Functional Training |  |  | Was 8/31
2009-07-27 | ODS functional training (Human Resources) | HR | S. Shaw | Functional Training | HR Technical & Reporting Team | Especially those working on reports | Now 8/3
2009-07-27 | LDIS - Technical Training (Remote) | LM |  | Remote | Luminis Technical Team | LMS Data Integration Focus | Now 7/6
2009-07-27 | Content Based Router Development | TN |  | Remote | Integration Team | ad hoc questions | Added
2009-08-03 | FI Go-Live Center - REMOTE | FI |  | Remote | Finance Team
2009-08-03 | ODS functional training (Human Resources) | HR | S. Shaw | Functional Training | HR Technical & Reporting Team | Especially those working on reports | Was 7/27
2009-08-03 | LDIS - System Verification & Test; Debugging Skills - On-site | LM |  | Functional Training | Luminis Technical Team | LMS Data Integration Focus | Now 7/13
2009-08-03 | LDIS - Knowledge Transfer (Functional Training) - On-site | LM |  | Functional Training | Luminis Technical Team | LMS Data Integration Focus | Now 7/13
2009-08-03 | Content Based Router Testing | TN |  | Remote | Integration Team | ad hoc questions
2009-08-03 | LDIS - Support | LM |  | Conference Calls | Integration Team |  | Was 9/7
2009-08-10 | FI Fixed Assets | FI | J. Langlois | Functional Consulting | Finance Team |  | Added
2009-08-10 | HR Topics TBD by Consultant and Client | HR | J. Greer | Functional Consulting | HR Core Team
2009-08-10 | ST General Student/Registration/Fee Assessment | ST | D. Marron | Functional Training | Student Team
2009-08-10 | FA Loans, Pell COD | FA | C. Linsley | Functional Training | Financial Aid Team
2009-08-10 | SUNC Onsite Implementation (Tentative) | TN | B. DeMillion | Installation | System Administrators |  | Added
2009-08-10 | Content based Router Knowledge Transfer | TN |  | Technical Consulting | Integration Team
2009-08-17 | FI Initial Budget Load and Spreadsheet Budgeting | FI | J. Langlois | Functional Training | Finance Team | Budget Focus
2009-08-17 | HR Progress Assessment - REMOTE | HR | TBD | Remote | HR Team Leader
2009-08-17 | FA Advisory Week 3 | FA | C. Linsley | Functional Consulting | Financial Aid Core Team
2009-08-17 | Financial Aid Conversion Support Session | FA | K. Whitelaw | Technical Consulting | Financial Aid Technical Team | Core Team needed for data review
2009-08-17 | SUNC Resting Support (Tentative) | TN | B. DeMillion | Installation | System Administrators |  | Added
2009-08-17 | Moodle & Sakai Integration Consulting | TN |  | Technical Consulting | Staff responsible for integration to LMS's |  | Now 6/29
2009-08-24 | Financial Aid Conversion Follow up (Remote) | FA | K. Whitelaw | Technical Consulting | Financial Aid Technical Team | Core Team needed for data review
2009-08-31 | FI Advisory Week 5 | FI | A. Fazul | Functional Consulting | Finance Core Team |  | Cancelled
2009-08-31 | HR Foundation Testing II using Test 100 Population | HR | J. Greer | Functional Training | HR Team
2009-08-31 | ST Accounts Receivable Training 1 | ST | D. Marron | Functional Training | Student Team | A/R Focus | Moved to 9/7
2009-09-07 | Human Resources Conversion Support Session | HR | L. Heineman | Technical Consulting | HR Technical Team | Core Team needed for data review
2009-09-07 | ST Accounts Receivable Training 1 | ST | D. Marron | Functional Consulting | Student Core Team |  | Was 8/31
2009-09-07 | FA FISAP, Holds, Messages, Self-Service | FA | C. Linsley | Functional Training | Financial Aid Team
2009-09-07 | Financial Aid Support Session for SAP, Institutional Aid, Comments Migration | FA | K. Whitelaw | Functional Training | Financial Aid Technical Team
2009-09-07 | LDIS - Support | LM |  | Remote | Luminis Technical Team | LMS Data Integration Focus | Now 7/20
2009-09-07 | EDW Production Install | IA | R. Williams | Remote | Reporting Team | Tech Staff for DW
2009-09-14 | FI Fixed Assets | FI | A. Fazul | Functional Training | Finance Team | Fixed Assets Focus | Cancelled
2009-09-14 | HR Foundation Testing III using Test 100 Population | HR | J. Greer | Functional Consulting | HR Core Team
2009-09-14 | Student Support Session for Accounts Receivable | ST | D. Jones | Technical Training | Student Technical Team
2009-09-21 | FI Progress Assessment and Lessons Learned - REMOTE | FI | G. Houck | Remote | Finance Team Leader
2009-09-28 | FI Advisory Week 6 | FI | A. Fazul | Functional Consulting | Finance Core Team
2009-09-28 | HR Budget Prep/Fiscal Year End (Fiscal Year Rolls, Salary Planner) | HR | J. Greer | Functional Training | HR Team
2009-10-05 | ST Academic History | ST | D. Marron | Functional Training | Student Team | Academic History Focus
2009-10-12 | FI Year End - REMOTE | FI |  | Functional Training | Finance Team |  | Now 3/8/10
2009-10-12 | FA Pre-go live consulting, New Year Roll | FA | C. Linsley | Functional Consulting | Financial Aid Core Team
2009-10-12 | ST Advisory Week 6 | ST | D. Marron | Functional Consulting | Student Core Team |  | Added
2009-10-12 | Banner Student Support Session for Academic History | ST | D. Jones | Technical Consulting | Student Tech Team
2009-10-19 | HR Parallel Testing I | HR | J. Greer | Functional Training | HR Team
2009-10-19 | ST Accounts Receivable Consulting 2 | ST | D. Marron | Functional Training | Student Team | A/R Focus
2009-10-19 | FA Advisory Week 4 | FA | C. Linsley | Functional Consulting | Financial Aid Core Team
2009-10-26 | HR Progress Assessment | HR | TBD | Conference Call | HR Team Leader
2009-10-26 | Student Conversion Support (Remote) | ST | D. Jones | Remote | Student Technical Team
2009-10-26 | ST Progress Assessment - REMOTE | ST | TBD | Conference Call | Student Team Leader
2009-11-02 | HR Advisory Week 3 - Rolling the Budget Test/Practice | HR | J. Greer | Functional Consulting | HR Core Team
2009-11-02 | ST Advisory Week 7 | ST | D. Marron | Functional Consulting | Student Core Team
2009-11-02 | ODS - Conduct functional training (Financial Aid) | FA | J. Keys | Functional Training | Financial Aid Reporting Team
2009-11-02 | SUNC Production Migration Support (Tentative) | TN | B. DeMillion | Remote | System Administrators |  | Added
2009-11-09 | FI Advisory Week 7 | FI | A. Fazul | Functional Training | Finance Core Team |  | Cancelled
2009-11-09 | ST Self Service - Student and Faculty and Advisors | ST | D. Marron | Functional Training | Student Team | SSB Focus
2009-11-16 | HR Go Live Readiness - Business Process Review and 2nd parallel | HR | J. Greer | Functional Consulting | HR Core Team
2009-11-16 | ST Consulting – Admissions Simulation | ST | D. Marron | System Testing | Student Team
2009-11-16 | EDW - Conduct technical and application training | IA | J. Keys | Technical Training | Reporting Technical Team
2009-11-23
2009-11-30 | HR Advisory Week 4 | HR | J. Greer | Functional Consulting | HR Core Team
2009-11-30 | ST EDI Functional Training | ST | D. Marron | Functional Training | Student Team
2009-12-07 | ST Simulation Go Live | ST | D. Marron | System Testing | Student Team
2009-12-14 | HR Advisory Week 5 | HR | J. Greer | Functional Consulting | HR Core Team
2009-12-14 | ODS - Conduct functional training (Student) | ST | J. Keys | Functional Training | Student Reporting Team
2009-12-21
2009-12-28
2010-01-04 | HR Go Live - REMOTE VIA Go Live Center | HR | J. Greer | Remote | HR Team
2010-01-11 | HR Go Live Support - REMOTE | HR |  | Remote | HR Team
2010-01-18 | HR Go Live Support - REMOTE | HR |  | Remote | HR Team
2010-01-18 | HR Progress Assessment and Lessons Learned - REMOTE | HR | TBD | Conference Call | HR Team Leader
2010-01-18 | AD Project Planning - Remote | AD | M. Hart | Conference Call | Advancement Team Leader
2010-01-18 | DW - Conference call to review timelines, implementation methodology and documents (may schedule later) | ST |  | Conference Call | Student Core Team | DegreeWorks Planning Call
2010-01-25 | HR Go Live Support - REMOTE | HR |  | Remote | HR Team
2010-01-25 | ST Advisory Week 9 | ST | D. Marron | Functional Consulting | Student Core Team
2010-01-25 | Student Conversion Support Session | ST | D. Jones | Technical Consulting | Student Technical Team
2010-01-25 | FA Advisory Week 5 | FA | C. Linsley | Functional Consulting | Financial Aid Core Team
2010-01-25 | DW - Review pre-install checklist with client | ST |  | Conference Call | Student Technical Team
2010-01-25 | DW - Begin Catalog Authentication | ST |  | Authentication Activity | Student Team | Instructional Support Activity
2010-02-01 | FI Advisory Week 8 | FI | A. Fazul | Functional Consulting | Finance Core Team |  | Cancelled
2010-02-01 | HR Go Live Support - REMOTE | HR |  | Remote | HR Team
2010-02-01 | HR Advisory Week 6 | HR | J. Greer | Functional Consulting | HR Core Team
2010-02-01 | AD Kickoff, Navigation, General System Overview, Shared Data & Interfaces, Reports | AD | M. Hart | Functional Consulting | Advancement Team | 1st Advancement Training Session
2010-02-08 | HR Go Live Support - REMOTE | HR |  | Remote | HR Team
2010-02-08 | ST System Go Live Center - REMOTE | ST |  | Remote | Student Team
2010-02-15 | ST Advisory Week 10 – Registration Simulation (Mock Reg) | ST | D. Marron | Functional Consulting | Student Core Team
2010-02-15 | EDW - Conduct Testing Session 1 | IA | J. Keys | System Testing | Reporting Technical Team
2010-02-22
2010-03-01 | FA Go Live consulting - REMOTE VIA GO LIVE CENTER | FA | C. Linsley | Remote | Financial Aid Team
2010-03-01 | AD Advancement Individuals, Organizations, Geographic Regions, Interface with Banner Student | AD | M. Hart | Functional Training | Advancement Team
2010-03-01 | EDW - Conduct Testing Session 2 | IA | J. Keys | System Testing | Reporting Technical Team
2010-03-08 | DW - SGHE reviews catalog requirements and provides scribing recommendations | ST |  | Conference Call | Student Team | Instructional Support Focus
2010-03-08 | FA Advisory Week 6 | FA | C. Linsley | Functional Consulting | Financial Aid Core Team
2010-03-08 | AD Milestone Review - REMOTE | AD |  | Remote | Advancement Team Leader
2010-03-08 | FI Year End - REMOTE | FI | J.Langlois | Functional Training | Finance Team |  | Was 10/12/09
2010-03-15 | DW - FHDA begins scribing catalog | ST |  | Catalog Scribing | Student Team | Instructional Support Focus
2010-03-15 | ST Progress Assessment 3 - REMOTE | ST | TBD | Conference Call | Student Team Leaders
2010-03-22
2010-03-29 | FA Milestone Review and Lessons Learned | FA | C. Marcotte | Conference Call | Financial Aid Team Leader
2010-03-29 | AD Campaigns and Designations, Basic Gift and Pledge Processing | AD | M. Hart | Functional Training | Advancement Team
2010-04-05
2010-04-12
2010-04-19 | AD Advancement Technical Training | AD | M. Hart | Technical Training | Advancement Technical Team
2010-04-26
2010-05-03 | ST Advisory Week 11 | ST | D. Marron | Functional Consulting | Student Core Team
2010-05-03 | FA Advisory Week 7 | FA | C. Linsley | Functional Consulting | Financial Aid Core Team
2010-05-10 | AD Consulting on Advancement Individuals, Organizations, Campaigns, Designations, Interfaces, Security, Rules | AD | M. Hart | Functional Training | Advancement Team
2010-05-17 | Advancement Data Mapping Session | AD |  | Technical Consulting | Advancement Technical Team
2010-05-24
2010-05-31 | DW - SGHE installs DW Software | ST |  | Remote | IT Core Team
2010-05-31 | AD Advanced Gift and Pledge, HR Interface, Matching Gifts, Third Party Payments | AD | M. Hart | Functional Training | Advancement Team
2010-06-07 | ST Advisory Week 12 | ST | D. Marron | Functional Consulting | Student Core Team
2010-06-07 | DW - Project Kickoff and Technical Training | ST |  | Consulting | Student Team | Tech Staff for DW
2010-06-14 | DW - Training 1 - Scribe and functional review process training | ST |  | Functional Training | Student Team | Instructional Support Focus
2010-06-14 | AD Transition Planning, Reporting Strategy | AD | M. Hart | Functional Consulting | Advancement Team
2010-06-21
2010-06-28 | AD Prospect Management, Advancement Self Service, Solicitor Organizations, Gift Society Processing | AD | M. Hart | Functional Training | Advancement Team
2010-07-05
2010-07-12
2010-07-19 | DW - Training 2 - Web functionality, access permissions | ST |  | Functional Training | Student Team | Instructional Support Focus
2010-07-26
2010-08-02 | Conduct ODS functional training (Advancement) | AD |  | Functional Training | Advancement Rptg. Team
2010-08-09
2010-08-16 | DW - Training 3 - Web localizations, Open issue resolution, Student Educational Planner | ST |  | Functional Training | Student Team | Instructional Support Focus
2010-08-16 | AD Transition Planning, Reporting Strategy | AD | M. Hart | Functional Training | Advancement Team
2010-08-23
2010-08-30 | Advancement Conversion Support Session | AD |  | Technical Consulting | Advancement Technical Team
2010-09-06 | ST Advisory Week 13 | ST | D. Marron | Functional Consulting | Student Core Team
2010-09-13
2010-09-20 | AD Job Submission, Population Selection, Letter Generation, Acknowledgments | AD | M. Hart | Functional Training | Advancement Team
2010-09-27
2010-10-04
2010-10-11 | HR Advisory Week 7 | HR | J. Greer | Functional Consulting | HR Core Team
2010-10-18 | AD Remote Assessment 2 | AD |  | Conference call | Advancement Team Leader
2010-10-25
2010-11-01
2010-11-08 | AD Memberships, Event Management and Data Extract and Load Process | AD | M. Hart | Functional Training | Advancement Team
2010-11-15
2010-11-22
2010-11-29 | AD Topics Based on Client Need – Pre Go Live Consulting | AD | M. Hart | Functional Consulting | Advancement Team
2011-01-03 | AD Go Live Support | AD | M. Hart | Functional Consulting
2011-01-31 | AD Milestone Review and Lessons Learned - REMOTE | AD |  | Remote | Advancement Team Leader