## Sheet1
Technology Strategic Plan Implementation Matrix
Student Access and Success
Goal #1: Use information technology to enhance access, learning, retention, and overall student success.
| Strategy | Responsible party | Current Status | Timeframe | Notes | Estimated Budget Impact | Priority | Implemtation action(s)
1.1 | Establish a realistic baseline level of access to computers for students, faculty and staff that includes a program for upgrading/replacing computers and related equipment on a regular cycle. | ETAC | Not started | As part of Tech II plan will have total value of all equipment and can come up with overall cost/plan | TCO Model from Tech II Plan provides this information | Low to none, only time and labor | High as part of Tech II report | Results of Tech II plan should meet goal
Will complete as part of Tech II planning process
Accept ratios put forward in Tech II plan as baseline, but could exceed
Target 3-year refresh
1.2 | Establish an appropriate level of technical support for students (both on campus and those learning at a distance), faculty, and staff. | Dean, Learning Technologies |  | By end of June will have definitive plan for staffing levels | TCO Model from Tech II Plan and survey/assessment of students | Low to none | High as part of Tech II report | Results of Tech II plan should meet goal
Endorse Tech II guidelines for staffing based available funding
1.3 | Ensure that technology is universally accessible to all persons, including those with disabilities. | Chief Technology Officer, ETAC and DSPS at each campus |  | As part of Tech II process | Need to do district-wide assessment | Moderate | High as part of Tech II report | Process underway
Already believe in universal accessibility
Software site licenses universal but furniture at 10% level
Assess hardware implications, but funding may already be there for disabled
1.4 | Develop and implement methods to identify student needs related to the use of information technology in the curriculum, instruction, and in student support areas. | Dean, Learning Technologies | Not started | Fall, 2001 and then ongoing | Survey students (random sampling) | Low to none, only time and labor | Low | Use Tech II information to formulate policy and planning for future services.
1.5 | Develop and deliver student services using technology with attention to the variety of ways in which students can gain access to information and services, including web access. | Dean, Learning Technologies | TouchNet contract being negotiated | Fall, 2001 (for registration) | Lengthy project. TouchNet only a partial solution, but may lead to other implementations. Full completion dependent on new admin systems. | Moderate to high | High | Use Tech II information to formulate policy and planning for future services.
[5 empty] | Student access from off campus to services |  |  | Implement web-based registratoin ASAP
1.6 | Establish policies to ensure that campus computing resources are available for students when needed. (e.g., hours of the day and days of the week) | Dean, Learning Technologies with various Division Deans | Not started | Spring, 2001 | Some of this already in place as established by Division Deans, but rest will happen after new Dean is hired | Low to none, only time and labor | Low | Tech II efforts will help establich computing resource policies.
1.7 | Ensure that online resources have appropriate bandwidth and high availability. | Director of Systems & Networks | Ongoing, currently sufficient bandwidth but availability of more servers an issue | FY 01-02 | Pending hire of Director of Systems & Networks; case-by-case basis until then | Moderate addiontal cost | High | Hire Director of Systems and Networks; establish server policy wehen user feedback obtained; establish backup policy for servers when outages occur.
Classroom-Based Technology
Goal #2: Integrate information technology into classroom-based instruction as appropriate to increase access to information and to enhance student learning.
| Strategy | Responsible party | Current Status | Timeframe | Notes | Estimated Budget Impact | Priority | Implemtation action(s)
2.1 | Provide adequate technical support to assist faculty in the use of technology in the teaching and learning process, within and beyond the classroom. | Dean, Learning Technologies, ETAC Instructional Technology subcommittee | Begun | Ongoing | Expect growth demands in this area | Moderate to high, depending on level of commitment | High based on Tech II planning and funding assessment | Provide adequate technical support to assist faculty in the design, development, and use of technology in the teaching and learning process, including the use of web-based technology to extend learning and communication opportunities beyond the classroom
Assess where we are with this area as it is prescribed by Tech II
How does @ONE & CVC play into this?
2.2 | Identify new technologies and their potential applications to teaching and learning. | Dean, Learning Technologies |  | Ongoing |  | Low to none, only time and labor | Low, new Dean and staff should do this as a natural part of their jobs | Scan the technology environment to identify new technologies and their potential applications to teaching and learning.
2.3 | Establish realistic technical standards for classroom-based technology. | Dean, Learning Technologies, College Instructional Deans, and representatives of the Academic Senate |  | Ongoing | Draft document already developed and delivered to Gilbane for Measure E | Low to none | High based on Tech II planning and funding assessment | Establish realistic technical standards for classroom-based technology
Tech II guidelines apply
2.4 | Establish a plan to ensure an adequate number of workstations in both open and discipline-based computer labs and classrooms. | CTO, ETS staff, Smart card administrators. District librarians, and computer lab representatives |  |  | Covered by 1.1, 1.2, 1.3 | Low to none, only time and labor |  | Establish a plan to ensure an adequate number of workstations in both open and discipline-based computer labs and classrooms. Implement a print for pay solution district wide utilizing the student smart card and coin for district’s libraries and campus computer labs. Set up a pilot program in Foothill’s library to test the solution before full implementation.
2.5 | Provide for the maintenance and realistic upgrading of these workstations once they are installed. | Director, Client Services |  | Ongoing | Covered by 1.1, 1.2, 1.3 | High |  | Develop a plan for the maintenance and realistic upgrading of these workstations once they are installed.
Distance Learning
Goal #3: Develop and deliver high quality distance learning courses and programs designed to expand learning opportunities.
| Strategy | Responsible party | Current Status | Timeframe | Notes | Estimated Budget Impact | Priority | Implemtation action(s)
3.1 | Support faculty in the development and use of distance learning for instruction. | Dean, Learning Technologies & College Deans of Distance Learning | Begun | Ongoing |  | Moderate to high | High | Each college will provide appropriate staffing, budget, technical support, training, and other resources to encourage effective implementation and delivery of Distance Learning programs. Solicit feedback from faculty and students regarding satisfaction and effectiveness of support levels.
3.2 | Collect and disseminate “best practice” research related to all aspects of distance learning | Dean, Learning Technologies & College Deans of Distance Learning | Begun | Ongoing | Some already posted on ETS website and colleges’ DL sites | Low to moderate | Low | Review research data and select material for dissemination; Deans will make the material available to all Distance Learning instructors.
3.3 | Establish feedback mechanisms for gaining distance learning student input. | College Deans of Distance Learning in conjunction with Institutional Research | Not current | Ongoing | Tied to 3.5 | Low, only time and labor | Medium | Develop and administer feedback mechanisms to collect/assess/analyze student inputs. Survey students to develop feedback on both the programs and this population.
3.4 | Derive a process that delivers online services which are equal to on- campus services, as appropriate and needed. | Deans of Distance Learning and Student Services Administrators (include Library, Bookstore, etc) | Begun | Ongoing | Tied to 1.5 | Moderate | High | Consult with appropriate administrators for Each of the student support services; Determine what online services are available and which are not available; Develop a plan to offer those that are not available
3.5 | Recommend mechanisms to improve retention and persistence in both televised and online distance learning courses | College Deans of Distance Learning Instructional Deans, and Institutional Research | Begun | Begun | Tied to 3.3 | Low to moderate | High
[5 empty] | Tied to 3.3 |  |  | research successful techniques; Convene focus groups of Distance Learning instructors, administrators, and support people to discuss various options and their applicability to local programs; make recommendations to all Distance Learning faculty.
3.6 | Promote the use of online library resources to enhance instruction. | College Library Administrators, Director Information Systems, College Deans of Distance Learning | Begun | Ongoing | Ask DL Deans to attend ETAC for a report on each strategy and what they have been doing and what their priorities are for this list and other things, address campus autonomy issues | Variable |  | Provide information of materials on college online library resources to the Distance Learning faculty; Promote online library classes teaching online research techniques; Provide assistance to users of online library services
3.7 | Develop college-specific distance learning strategic plans. | College Deans of Distance Learning Instructional Deans, VP of Instruction/VP of Instruction & Technology/VP of Instructional & Research, & other appropriate managers. | Drafts currently under review | Fall 2001 |  | Moderate to high | Medium | Collaborate with other college administrators to develop a long term Distance Learning strategy ; Ensure that this plan is in harmony with district-wide technology plan and College Educational Masters Plans; Develop such a strategy and get it approved at each college using appropriate process
3.8 | Establish college policies and/or district policies as needed for distance learning courses. | College Deans of Distance Learning in consultation with shared governance groups. | Informal at the present, not consistent between divisions. | Spring 2002 | This will be challenging to bring to consensus, as evidenced by recent meetings on intellectual property rights. Also impacted by contractual agreements and varies by division on issues such as class size. | Low to moderate | Medium | Work with the appropriate parties to create a district policy for Distance Learning. Implement policies regarding courses and programs; e.g. maximum class size, intellectual property rights, etc
3.9 | Establish college standards and/or district standards as needed for distance learning courses. | College Deans of Distance Learning, Dean, Learning Technologies, Instructional Deans, VP of Instruction/VP of Instruction & Technology/VP of Instructional & Research, Academic Senates, & Faculty Assn. | Pending | Spring 2002 | Tied to 4.1 Must be done in consultation with Distance Learning faculty. | Moderate | Medium | Develop standards for quality of materials to be used in Distance Learning courses. Develop standards for quality delivery.
Administrative Efficiency
Goal #4: Install and maintain appropriate levels of information technology throughout the district, including information technology systems that support the
business of the district and that provide meaningful data for decision-making.
| Strategy | Responsible party | Current Status | Timeframe | Notes | Estimated Budget Impact | Priority | Implemtation action(s)
4.1 | Continuously monitor user and community needs to assess system requirements as they evolve. | IS director | Not started | Ongoing | Use committees to address these issues | Low | 1 | set up an advisory group; poll user community on regular basis; conduct open forums; create and update a needs assessment from which procurement alternative can be investigated
Should have at least one ETAC open forum this year as part of Tech II plan to give info (May/June) through Town Halls and College Hours
4.2 | Provide the system and infrastructure (hardware, software, and tools) to the users to enable meaningful decision making and communication to take place. | IS director and Network Services Director | Network HW in place. MIS upgrade not started | Ongoing |  | High | 2 | develop, update and maintain the technical infrastructure required to provide the services in 4.1; develop and support a district-wide institutional research database; develop and support the software tools needed by all users; contribute to the MIS portion of the comprehensive district disaster plan
4.3 | Develop standards for client services, including desktop hardware and software as well as a strategy for technology upgrades. | Director of Client Services | Version 1 in place/ upgrade in process | Ongoing |  | Medium / High | Very High | establish and update standards for client (desktop) hardware; establish and update standards for client (desktop) software; develop and implement a plan to update all technology within the district on a regular and predictable schedule
|  |  | “Oracle” project moving along |  | New director soon to be hired |  |  | establish and update standards for client (desktop) software;
develop and implement a plan to update all technology within the district on a regular and predictable schedule
4.4 | Propagate better utilization of the available tools through training and communication | CTO in conjunction with ETS management and ETAC | In process | Ongoing | Tied to 4.3 | Medium | 4 | develop and implement a training plan for all user-pertinent items;
[5 empty] | Don’t need to promote because demand already there |  |  | develop and implement a training plan for all user-pertinent items; publicize what is 'available' through division meetings & other internal communication tools (the ETS newsletter?)
Professional Development
Goal #5: Develop and implement ongoing technology-related professional development and training programs for all full- and part-time
faculty and staff.
| Strategy | Responsible party | Current Status | Timeframe | Notes | Estimated Budget Impact | Priority | Implemtation action(s)
5.1 | Develop and implement methods for obtaining faculty and staff input related to technology training needs and issues. | Technology Trainers | In process | Fall term | Delegate assessment to Dean, Learning Technologies and trainers, with Institutional Research. Tied to 2.1 | 100 | High | Trainers will develop a survey form. Distribute survey in fall term Need to Coordinate with IR
5.2 | Provide ongoing and current information to all faculty and staff about what technology is currently available throughout the district and how to access it. | CTO and Dean of Learning Technologies | Exists on ETS web site and promotions in Newsbytes | Ongoing | Trainers, newsletter, ETS site |  | High for Dean of Learning Technologies | Already on ETS web site and Newsbytes
5.3 | Create an ongoing year-round, district-wide training program that offers a variety of alternatives (delivery mode, scheduled times and days) in which professional development and training can be obtained and that includes training on both administrative and academic technologies and applications. | Dean of Learning Technologies and trainers | Has been happening for years now. | Ongoing |  |  | High | Already implemented, but will be modified based on needs analysis.
5.4 | Identify basic technology skill-levels for faculty and staff, and provide training opportunities for attaining these levels. | Dean of Learning Technologies, trainers and Instructional Tecnology Sub Committee of ETAC | CTO discussions with vice chancellor re: new staff orientation | Fall term | Tied to 5.1 |  | Medium | Instructional Technology subcommittee will identify basic technology skill-levels for faculty and staff.
[5 empty] | Establish basic standard for knowledge (similar to district HW/SW standards) |  |  | Trainers will provide training opportunities.
5.5 | Provide training on technology tools and applications for discipline and job specific needs. | Dean of Learning Technologies | On back burner |  | Lower priority than basic technology skills for staff |  | Medium | ETS managerment will identify need and trainers will provide discipline- and job-specific training on technology tools and applications.
5.6 | Provide information and specific training related to policies associated with ADA requirements, fair-use copyright law, intellectual property, and other pertinent legal issues as these relate to technology use in the district. | CTO in consultation with FA, DSS and district legal staff and Deans of Distance Learning | Unknown |  |  |  | Medium | ETS management will identify need and trainers will provide training.
5.7 | Establish and support a mentoring program for faculty and staff regarding the use of technology in their assignment. | Dean of Learning Technologies | Unknown |  |  |  | Low | ETS Management will work with ETAC to establish this program.
5.8 | Develop and implement technology-related incentive and recognition programs for faculty and staff. | Dean of Learning Technologies and College Instructional Deans | Unknown |  |  |  | Low | ETS Management will work with ETAC to establish this program.
Communication
Goal #6: Use information technology strategically to facilitate effective communication and open access to information.
| Strategy | Responsible party | Current Status | Timeframe | Notes | Estimated Budget Impact | Priority | Implemtation action(s)
6.1 | Develop a District Communication Plan that promotes the use of technology, internally and externally, through the use of the Internet, intranet, Web, email, phones, remote access, etc. | CTO and ETAC web subcommittee |  | ETS site operational and some intranet service, but little else other than external site | Use ETS as a model |  | High | Establish an ad hoc ETAC subcommittee, which would include representatives from ETAC, the campus-level web advisory committees, and ETS. Establish goals and objectives. Invest and plan for alternatives to expand off-campus access to District communications resources. Establish standards and design specifications for District-wide communications between all of the constituencies (administration, faculty, staff, and students). Establish and communicate policies.
6.2 | Design, provide, and maintain the physical infrastructure and staffing necessary to accomplish the goals established in the District Communication Plan. | CTO mind dump |  |  | Dependent on funds for staffing |  | High | Analyze the existing physical infrastructure and staffing, in order to accomplish the goals established in the District Communication Plan. Prioritize and budget for future needs. Develop feedback and communication vehicles to user community
6.3 | Provide continuing training for people who are using the communication technologies established in the District Communication Plan. | Dean of Learning Technologies, Staff Development, College Webmasters, Division representatives |  |  |  |  | High | Analyze and respond to training needs across the District. Offer classes to teach people how to use the communicationtechnologies. Provide technical liaison between ETS and each Division, program or Department to determine ongoing needs and solutions. Develop feedback and communication vehicles to user community.
6.4 | Assure reliable access to the communications technologies. | ETS | Planning process beginning | Next year | Cannot begin implementation until after ETS completion of TouchNet and cluster upgrade |  | Medium | Provide continuing technical support to the users. Develop feedback and communication vehicles to user community.
6.5 | Create and communicate a district-wide information technology appropriate use policy for administration, faculty, staff, and students. | ETS and ad hoc ETAC subcommittee | In place, a few years old |  | Put on ETS web site |  | Medium | Review and revise the existing Distract-wideinformation technology appropriate use policy and communicate the updated policy to administration, faculty, staff, and students.
Fiscal Resources
Goal #7: Allocate an appropriate portion of general funds for information technology as part of a comprehensive long-range plan for
achieving the district mission.
| Strategy | Responsible party | Current Status | Timeframe | Notes | Estimated Budget Impact | Priority | Implemtation action(s)
7.1 | Develop a multi-year technology implementation plan, incorporating Total Cost of Ownership (TCO) concepts into the acquisition and support of information technology and including budgetary requests for regular upgrading of facilities and equipment. | Chief Technology Officer |  |  | Efforts for Tech II planning will provide a basis for current status and a blueprint for directions in the future. |  | High | Colleges currently working on Tech II implementation planning. ETS managers will support planning effort and the development of TCO plan. ETAC will review and advocate for plans.
7.2 | Prioritize information technology spending in accordance with institutional goals, making choices that can be adequately funded on an ongoing basis by identified and allocated funds. | Chief Technology Officer and ETAC |  |  | Tech II planning, need to have ETAC subcommittee or committee of the whole; have a specified time for budget report to ETAC |  | High | ETS managers, working through their respective subcommittees, can bring initiatives forward to CTO and ETAC for prioritization and advocacy.
7.3 | ETS will thoroughly analyze the cost of any new project and must receive funding prior to implementation. | Chief Technology Officer |  |  |  |  | High | ETS managers will do cost analysis for any new project and advocate through district processes for funding before beginning new projects
7.4 | Investigate and implement district-wide software licensing agreements as appropriate. | Director, Client Services | Already implemented | Ongoing |  |  | High | Hardware/Software Standards committee establishes district software standards for which ETS managers can then negotiate licenses
7.5 | Develop long-term agreements with local business/industry to support and provide resources. | Chief Technology Officer |  |  |  |  | Low | Current grants and contracts policy under consideration by ETAC should be sufficient once officially approved.
Information Technology Organization and Governance
Goal #8: Establish and communicate an appropriate organizational structure for Educational Technology Services (ETS) and an
appropiate information technology organization structure for the district with major responsibility for prioritizing information technology with
district and college Educational Master Plan
| Strategy | Responsible party | Current Status | Timeframe | Notes | Estimated Budget Impact | Priority | Implemtation action(s)
8.1 | Establish and clearly define the role and membership of the Educational Technology Advisory Committee (ETAC) as the technology advisory group to the Chancellor’s Advisory Committee (CAC) and the Chancellor. | ETAC | Completed | Ongoing | See ETAC web postings | No impact | High
8.2 | Establish appropriate user groups and provide a communication path for advice and input on technology issues from these groups and other users to Educational Technology Services (ETS). | ETAC | Not created yet. | Ongoing | Self starting groups, with facilitation by ETS. | Need for server and software and some management thereof. Some ETS staff time to act as liaisons to groups. | High | Identify need and establish groups. Recognize groups that already exist. Assist communication to reduce duplication. Set up listservs. One ETS staff member would be part of each group.
Set up listserv strategy for encouraging group communication
8.3 | Establish appropriate sub-committees for the Educational Technology Advisory Committee (ETAC) to provide governance advice. | ETAC | Subcommittees created, membership needed |  | Committees in place will meet as ETS managers come on board | None | High | Discuss implementation steps in ETAC before end of spring, 2001 quarter
8.4 | Directly link information technology projects and initiatives to district and college Educational Master Plans. | ETAC |  | Ongoing |  | None, except for staff and meeting times | High | Internal ETAC process needs to be worked out. No retroactive action, but prioritization of future plans/projects will need to be matched to master plans
8.5 | Establish and implement consistent information technology project management systems with feedback loops for gathering and disseminating information about project status. | ETAC & Chief Technology Officer, with ETS managers |  |  | Will use appropriate communication methods for informing community about project status |  | High | ETS managers will develop projects based on active user input and use project management principles to manage ETS projects
8.6 | Develop and communicate methods for initiation, approval, prioritization, and completion of information technology projects. | ETAC & Chief Technology Officer |  |  | Incorporate into program review process. ETAC will be involved in process |  | High | Process for communication prioritization, and rationale for ETS services should be put into place with joint effort of ETS managers and ETAC
8.7 | Establish and communicate information technology-related policies, including intellectual property agreements, licensing agreements, standards, guidelines, remote access, etc. |  |  |  | Subcommittee for some of these issues, which will be operational with new managers in the fall |  | High | ETS managers will activate each subcommittee and get them operational in Fall, 2001
8.8 | Establish the procedure by which the Educational Technology Advisory Committee (ETAC) reviews recommendations from Educational Technology Services (ETS) regarding staff size and/or reorganization of existing staff. | ETAC & Chief Technology Officer |  |  | Reorganizations of staff needs to be reviewed under normal district procedures; projects with budget implications go through district budget processes; ETAC will be regularly informed of this information; ETS & ETAC will develop review process |  | High | ETAC would serve as conduit for informing ETS managers of user needs; ETAC would serve as advocacy group on behalf of ETS and district technology needs, as appropriate
8.9 | Develop in-house training programs to enable technology professionals to be promoted within the district. | Chief Technology Officer & ETS managers |  |  |  |  | Low | ETS will develop in-house training programs to enable technology professionals to be promoted within the district.
8.10 | Update the information technology strategic plan annually (first review to be completed by April 1, 2002) for timely input into the District budget process. | ETAC & Chief Technology Officer |  | Next year (01-02) | Is the date appropriate? |  | Medium/Low | The information technology strategic plan will be reviewed annually (first review to be completed by April 1, 2002) for timely input into the District budget process.
Last updated 6/27/01